## plan
Section | Item | Detail | Note
1. OVERVIEW
| Project | KAITAI / 解体する (working title) - 1-4 player co-op kaiju demolition
| Milestone | MVP - reduced from GDD ch.12
| Window | Mon 21 Sept - Wed 30 Sept 2026 | 8 working days
| Working days | 21, 22, 23, 24, 25 Sept + 28, 29, 30 Sept | Weekend 26-27 excluded
| Ship date | Wed 30 Sept 2026 | No buffer day
| Team | 2 developers + 2 3D modellers, dedicated to KAITAI | Confirm exact composition
| Source spec | 解体する（仮）Core Loop & Base Specification v0.3 | 2026-09-19
| Central hypothesis (ch.15) | Interrupting simple legible demolition with unpredictable but manageable incidents preserves the pleasure of the work and creates a reason to replay. | Everything below serves this
2. STUDIO AUDIT - WHAT ACTUALLY EXISTS
| There is no KAITAI place | Only 'Escape From Pirate (Dev)' is open in Studio. No laser cutter, drone, gas mask, survivor or demolition-% system exists anywhere. | Day 1 starts with a new place
| A usable prototype DOES exist, in the wrong place | Built 19 Sept inside the pirate place: a cube kaiju with breakable blocks, buried organs, and a working toxic-gas hazard. | Port it, do not rebuild it
| KaijuBlockBuilder (ModuleScript, 10.4KB) | Signed-distance field to 4-stud cubes. 16,251 cells, only ~29% spawned as Parts via lazy reveal; breaking a block spawns its neighbours. BreakAt(pos, radius) API. | REUSE - the hardest single piece
| StomachGasHazard (Script, 7.5KB) | Gas bursts when an organ block is broken; HP drains while inside; re-arm cooldown; gas-mask bypass hook already wired. | REUSE - matches GDD 6.1 closely
| Block material split | SKIN / MEAT / BONE / ORGAN / EGG are already separate materials | This IS the normal-vs-event tagging GDD 5.3 + D7 require for drone exclusion
| KaijuBlocks + KaijuOrgans | 4,687 live cube Parts and 6 organ markers carrying a Hazard attribute | Reference data, will be regenerated
| Shape mismatch | The prototype kaiju is a quadruped, not the green octopus the GDD names as the MVP kaiju (FIG-08) | System reusable, skeleton must be re-authored
3. WHAT MAPS TO THE GDD
| Kaiju as climbable breakable terrain (1.1, FIG-02) | Cube system done | HAVE
| Cut flesh and bone (2, D1) | BreakAt wired to a tool | HAVE
| Event blocks buried inside (6) | Organs and eggs already distinct | HAVE
| Drone must not cut event blocks (5.3, D7) | Material tagging already separates them | HAVE - big saving
| Toxic gas event (6.1) | StomachGasHazard, incl. mask bypass | HAVE
| Gas mask 4 FOV tiers (6.1) | Bypass hook exists, no tiers or FOV effect | PARTIAL
| Demolition % and 100% clear (3.1, D3) | Not built, but the grid knows total vs remaining | BUILD - small
| Laser cutter, gun, 4-slot inventory (4) | Nothing | BUILD
| Support drone (5) | Nothing | BUILD
| Eggs to larvae (6.2) | Egg blocks exist, no larvae | BUILD
| UFO laser (6.4) | Nothing | CUT from MVP - see section 5
| 1-4 co-op (3.1, D2) | Nothing | BUILD
| HUD (9.1) | Nothing | BUILD
| Lobby and shop (11.1) | Nothing | BUILD - minimal
| HP, no regen, healing (D4) | Gas already damages HP | PARTIAL
4. LOCKED BY THE GDD (ch.13)
| D1 Base | Mountain-flattening work loop, mountain replaced by a kaiju corpse
| D2 Party size | 1-4; kaiju difficulty does NOT scale for solo
| D3 Clear | 100% demolition
| D4 Health | HP exists, zero ends the run, no passive regeneration
| D5 Loadout | Mask, gun, cutter; 4 slots, slot 4 reserved and empty at launch
| D6 Automation | Turrets dropped; support drone only
| D7 Drone limits | Ordinary flesh and bone only, never event blocks
| D8 Ammo | Unlimited
| D9 Tool separation | Cutter does no damage to enemies; gun does not cut the kaiju
| D10 Differentiation | Random events and how they compound ARE the product
5. IN SCOPE - 8-DAY MVP
| Kaiju | 1 - green octopus, re-authored on the existing cube system | GDD FIG-08
| Map | 1 - ruined seaside city, grey-box plus a dressing pass | GDD 10.1
| Core | Demolition %, 100% clear, HP with no regen, healing item | D3, D4
| Tools | Laser cutter, gun, gas mask; 4 slots with slot 4 empty | D5
| Events | 2 of 3 - toxic gas (ported) and eggs to larvae (new) | 6.1, 6.2
| Drone | Support drone with event-block exclusion | D6, D7
| Co-op | 1-4 players, shared demolition % | D2
| HUD | Demolition %, HP, 4 slots, event warnings | 9.1
| Lobby | Deploy gate, shop (masks/guns/healing), one upgrade axis | 11.1
| Difficulty | NORMAL only | 3.2 reduced
| Instrumentation | K1-K9 logging so the prototype can actually answer ch.14 | ch.15
6. OUT OF SCOPE - DEFERRED
| UFO laser event | GDD lists it in MVP. No existing tech, needs telegraph VFX and a new AI. | CUT - needs client sign-off
| Survivors | Already deferred by the GDD | ch.12
| Alien invasion and portals | Already deferred by the GDD | ch.12
| Kaiju 2 and 3 | Already deferred | ch.12
| HARD / EXTREME tuning | NORMAL only for the prototype | 3.2
| Drone camera (9.2) | Gate on K6 - only build it if hunting the last 1% measures badly | 9.2
| Three upgrade axes | Cutting speed only; drone and gun axes later | 8.1 reduced
| Opening movie | Text mission brief instead | 10.2
| Suit recoloring, dailies, login bonus, codex | Retention features, post-launch | 11.2
7. MILESTONES
| Day 1 - Mon 21 Sept | New place stood up; cube system ported; demolition % counting
| Day 2 - Tue 22 Sept | Octopus kaiju in engine; laser cutter cuts it | First playable cut
| Day 3 - Wed 23 Sept | Gun, larvae, egg event working
| Day 4 - Thu 24 Sept | Gas ported with mask tiers; drone assisting | GO / NO-GO on co-op
| Day 5 - Fri 25 Sept | 1-4 co-op with shared %; HUD complete | Feature complete target
| Day 6 - Mon 28 Sept | Lobby, shop, upgrade axis, healing
| Day 7 - Tue 29 Sept | KPI logging; balance; full QA pass
| Day 8 - Wed 30 Sept | Bugfix and ship | SHIP
8. TEAM LOAD
| Dev A - gameplay systems | Cube port, demolition %, tools, HP, events, drone
| Dev B - world, co-op, UI | Map, networking, HUD, lobby, shop, QA
| Modeller 1 - kaiju and creatures | Octopus, larvae, drone model | Octopus is the long pole
| Modeller 2 - map, tools, props | Seaside city, cutter/gun/mask, hazmat suit
9. RISKS
| RESOLVED - team collision | Was: two MVPs on the same days with one team. KAITAI now has a dedicated team. | Closed 19 Sept
| HIGH - co-op networking | Nothing in the prototype is multiplayer. Shared demolition state across 4 clients is the riskiest new build. | Day 4 go/no-go; fallback is solo-only for the prototype
| HIGH - no buffer | Day 8 is release work, not slack | If Day 7 QA finds anything structural, cut the egg event
| MED - octopus authoring | The cube kaiju is defined by a hand-authored SDF skeleton; a tentacled octopus is harder to express than a quadruped | Budget 1.5 days; fallback is reusing the existing body shape reskinned
| MED - block count at scale | 4,687 Parts for one player; 4 players on one kaiju multiplies replication load | Measure on Day 5; lazy reveal already cuts 71%
| LOW - GDD numbers are provisional | Almost every value is tagged 仮 (provisional) | Build config-driven; ch.15 KPIs settle them
10. OPEN ITEMS
| O-A Team | Dedicated KAITAI team confirmed | CLOSED - 19 Sept
| O-B UFO event | GDD puts it in MVP; this plan cuts it. Client sign-off needed. | Needs answer by Day 3
| O-C N1 run length | Target length of one run - drives kaiju block count (N3) | Pick a provisional 15 min and measure
| O-D N6 death handling | Death, spectating, wipe conditions undefined | Needed before co-op work on Day 5
| O-E N7 UFO shootable | Moot if UFO is cut | Follows O-B
11. KPIs TO INSTRUMENT (ch.15)
| K1 Run completion rate | Whether length and difficulty are right
| K2 Clear time, overall and by party size | Feeds N1 and N2
| K3 Cutting time vs event time | Event frequency (N5) | Core hypothesis
| K4 Time to return to cutting after an event | Whether the short loop closes | Core hypothesis
| K5 Drone share of demolition | Feeds N4 - must stay below the player's own share
| K6 Time hunting the last 1% | Whether the drone camera is needed at all
| K7 Damage from switching to the wrong tool | Whether the switch UI works
| K8 Down rate solo vs co-op | Feeds N6 and difficulty design
| K9 Replay rate on the same kaiju | The central hypothesis | The one that matters most
12. DEFINITION OF DONE
| Primary | A 1-4 player run reaches 100% demolition and ends cleanly
| Primary | Both events fire, are survivable, and the player returns to cutting
| Primary | The drone assists and never destroys an event block (D7)
| Primary | Cutter does no damage to enemies; gun does not cut the kaiju (D9)
| Added | K1-K9 emit structured events so ch.14 can actually be answered
13. COLUMN LEGEND (tasks tab)
| Depends | Task IDs that must finish first. Blank means unblocked, can start on day one.
| Depends - multiple | A2, M1a' means both must land first.
| Depends - 'all' | The QA pass waits on everything, which is why it sits on Day 7.
| Spec | Where the requirement lives in the KAITAI GDD v0.3.
| Spec - D1 to D10 | Chapter 13 Decisions - treat as fixed premises, not suggestions.
| Spec - N1 to N10 | Chapter 14 Next Decisions - still open, build config-driven.
| Spec - K1 to K9 | Chapter 15 KPIs - what the prototype must measure.
| Spec - numbers | Section numbers, e.g. 6.1 = toxic gas, 5.3 = drone targeting.

## tasks
ID | Date | Day | Owner | Workstream | Task | Depends | Spec | Est h | Status
A1 | 2026-09-21 | 1 Mon | Dev A | Setup | Create the KAITAI place; folder structure; server-authoritative layout |  |  | 2 | Not started
A2 | 2026-09-21 | 1 Mon | Dev A | Kaiju | Port KaijuBlockBuilder from the pirate place; verify lazy reveal and BreakAt | A1 | 1.1 | 4 | Not started
A3 | 2026-09-21 | 1 Mon | Dev A | Core | Demolition % system: total vs remaining blocks, shared team value | A2 | D3 | 2 | Not started
B1 | 2026-09-21 | 1 Mon | Dev B | World | Grey-box the ruined seaside city; spawn area and deploy point | A1 | 10.1 | 5 | Not started
B2 | 2026-09-21 | 1 Mon | Dev B | Setup | Config modules: KaijuConfig, ToolConfig, EventConfig, DroneConfig | A1 |  | 3 | Not started
M1a | 2026-09-21 | 1 Mon | Modeller 1 | Art | Green octopus blockout - pose must give 2 climb routes and a mouth opening |  | 7.1 | 8 | Not started
M2a | 2026-09-21 | 1 Mon | Modeller 2 | Art | Hazmat suit + laser cutter + gun + gas mask models |  | 4.1 | 8 | Not started
A4 | 2026-09-22 | 2 Tue | Dev A | Kaiju | Re-author the SDF skeleton as the octopus; tentacles as paths and walls | A2, M1a | 7.1 | 6 | Not started
A5 | 2026-09-22 | 2 Tue | Dev A | Tools | Laser cutter: cuts blocks only, no damage to enemies | A2 | D9 | 3 | Not started
B3 | 2026-09-22 | 2 Tue | Dev B | Core | HP system: no passive regeneration, death ends the run | B2 | D4 | 3 | Not started
B4 | 2026-09-22 | 2 Tue | Dev B | World | Seaside city dressing pass 1; kaiju placement in the map | B1 | 10.1 | 5 | Not started
M1b | 2026-09-22 | 2 Tue | Modeller 1 | Art | Octopus detailing; tentacle forms; mouth interior | M1a | 7.1 | 8 | Not started
M2b | 2026-09-22 | 2 Tue | Modeller 2 | Art | Seaside city kit: buildings, docks, cranes, rubble |  | 10.1 | 8 | Not started
A6 | 2026-09-23 | 3 Wed | Dev A | Combat | Gun: unlimited ammo, damages enemies only, does not cut the kaiju | A5 | D8, D9 | 4 | Not started
A7 | 2026-09-23 | 3 Wed | Dev A | Events | Egg event: breaking an egg block spawns a larva that chases and damages | A2, M1c | 6.2 | 5 | Not started
B5 | 2026-09-23 | 3 Wed | Dev B | UI | 4-slot inventory; switching costs exactly one action; slot 4 empty | B2 | D5, 4.2 | 5 | Not started
B6 | 2026-09-23 | 3 Wed | Dev B | World | Dressing pass 2; climb routes and interior access verified on the kaiju | B4, A4 | 7.1 | 3 | Not started
M1c | 2026-09-23 | 3 Wed | Modeller 1 | Art | Kaiju larva creature + animations |  | 6.2 | 8 | Not started
M2c | 2026-09-23 | 3 Wed | Modeller 2 | Art | Support drone model; event-block VFX (organ glow, egg pulse) |  | 2026-05-06 | 8 | Not started
A8 | 2026-09-24 | 4 Thu | Dev A | Events | Port StomachGasHazard; retarget to any organ block | A2 | 6.1 | 3 | Not started
A9 | 2026-09-24 | 4 Thu | Dev A | Tools | Gas mask 4 tiers: FOV restriction trades against safety | A8, M2a | 6.1 | 4 | Not started
A10 | 2026-09-24 | 4 Thu | Dev A | Drone | Support drone: cuts ordinary blocks only, never event blocks | A2, M2c | D6, D7, 5.3 | 5 | Not started
B7 | 2026-09-24 | 4 Thu | Dev B | Co-op | Networking spike: replicate block destruction to 4 clients | A3 | D2 | 6 | Not started
M1d | 2026-09-24 | 4 Thu | Modeller 1 | Art | Octopus polish; LODs; block-break particle set | M1b |  | 8 | Not started
M2d | 2026-09-24 | 4 Thu | Modeller 2 | Art | Lobby environment; shop stalls; deploy gate |  | 11.1 | 8 | Not started
A11 | 2026-09-25 | 5 Fri | Dev A | Drone | Drone power calibration: contribution must stay below the player's | A10 | 5.4, N4 | 3 | Not started
A12 | 2026-09-25 | 5 Fri | Dev A | Events | Event roll policy: no immediate repeats, single events at low % | A7, A8 | 6.6 | 3 | Not started
B8 | 2026-09-25 | 5 Fri | Dev B | Co-op | 1-4 player co-op: shared demolition %, player list, join/leave | B7 | D2 | 6 | Not started
B9 | 2026-09-25 | 5 Fri | Dev B | UI | HUD: demolition % top, HP bottom-left, 4 slots bottom, event warnings at edges | B5 | 9.1 | 4 | Not started
M1e | 2026-09-25 | 5 Fri | Modeller 1 | Art | Creature polish; drone animation |  |  | 8 | Not started
M2e | 2026-09-25 | 5 Fri | Modeller 2 | Art | Map dressing pass 3; lighting and skybox |  | 10.1 | 8 | Not started
A13 | 2026-09-28 | 6 Mon | Dev A | Progression | Healing items brought from the lobby; found inside the kaiju | B3 | 3.1, 8.2 | 3 | Not started
A14 | 2026-09-28 | 6 Mon | Dev A | Progression | One upgrade axis: cutting speed; persistence of purchases | B2 | 8.1 | 4 | Not started
B10 | 2026-09-28 | 6 Mon | Dev B | Lobby | Lobby: deploy gate, kaiju select, difficulty (NORMAL only) | B8 | 11.1 | 4 | Not started
B11 | 2026-09-28 | 6 Mon | Dev B | Lobby | Shop: gas mask tiers, guns, healing items | A9, A14 | 8.2 | 4 | Not started
M1f | 2026-09-28 | 6 Mon | Modeller 1 | Art | Fix pass; any missing creature states |  |  | 6 | Not started
M2f | 2026-09-28 | 6 Mon | Modeller 2 | Art | UI art: HUD frames, icons, warning graphics | B9 | 9.1 | 8 | Not started
A15 | 2026-09-29 | 7 Tue | Dev A | Telemetry | Instrument K1-K9; structured event logging | all | ch.15 | 5 | Not started
A16 | 2026-09-29 | 7 Tue | Dev A | Balance | Tune cutting speed, event frequency, larva strength to a completable run | A12 | N1, N5 | 3 | Not started
B12 | 2026-09-29 | 7 Tue | Dev B | QA | Full pass: solo and 4-player, both events, drone rules, tool separation | all |  | 6 | Not started
B13 | 2026-09-29 | 7 Tue | Dev B | UX | Text mission brief replacing the opening movie | B10 | 10.2 | 2 | Not started
M1g | 2026-09-29 | 7 Tue | Modeller 1 | Art | QA fix pass | B12 |  | 8 | Not started
M2g | 2026-09-29 | 7 Tue | Modeller 2 | Art | QA fix pass | B12 |  | 8 | Not started
A17 | 2026-09-30 | 8 Wed | Dev A | Release | Bugfix from QA | B12 |  | 6 | Not started
A18 | 2026-09-30 | 8 Wed | Dev A | Release | Verify D7 (drone never cuts event blocks) and D9 (tool separation) hold | A17 | D7, D9 | 2 | Not started
B14 | 2026-09-30 | 8 Wed | Dev B | Release | Re-run QA; publish config; place settings | A17 |  | 6 | Not started
B15 | 2026-09-30 | 8 Wed | Dev B | Release | Confirm K1-K9 are emitting real data from a full run | A15 | ch.15 | 2 | Not started
M1h | 2026-09-30 | 8 Wed | Modeller 1 | Art | Final polish |  |  | 8 | Not started
M2h | 2026-09-30 | 8 Wed | Modeller 2 | Art | Final polish |  |  | 8 | Not started
CUT | - | - | - | Deferred | UFO laser event - GDD has it in MVP, cut here |  | 6.4 |  | Needs sign-off
CUT | - | - | - | Deferred | Survivors event |  | 6.3 |  | Cut from MVP
CUT | - | - | - | Deferred | Alien invasion and portals |  | 6.5 |  | Cut from MVP
CUT | - | - | - | Deferred | Kaiju 2 and 3 |  | 7.1 |  | Cut from MVP
CUT | - | - | - | Deferred | HARD / EXTREME difficulties |  | 3.2 |  | Cut from MVP
CUT | - | - | - | Deferred | Drone camera - gate on K6 |  | 9.2 |  | Cut from MVP
CUT | - | - | - | Deferred | Drone and gun upgrade axes |  | 8.1 |  | Cut from MVP
CUT | - | - | - | Deferred | Opening movie, dailies, login bonus, kaiju codex |  | 10.2, 11.2 |  | Cut from MVP

## All Tasks
ID | Phase | Group | Task | Spec | Status | MVP | MVP task | Note
SET-01 | — | SET 基盤/セットアップ | KAITAIプレイスの新規作成・フォルダ構成・サーバー権威レイアウト | — | 決定 | ○ | A1
SET-02 | — | SET 基盤/セットアップ | KaijuBlockBuilderを海賊プレイスから移植（lazy revealとBreakAtの動作確認） | 1.1 | 決定 | ○ | A2 | 16,251セル中29%のみPart化。最も難しい部品を再利用できる
SET-03 | — | SET 基盤/セットアップ | Configモジュール（KaijuConfig / ToolConfig / EventConfig / DroneConfig） | — | 決定 | ○ | B2
SET-04 | — | SET 基盤/セットアップ | 全数値をConfig駆動にする | 0 | 仮 | ○ | B2 | GDDの数値はほぼ全部【仮】。ch.15の計測で確定する
SET-05 | — | SET 基盤/セットアップ | KaijuBlocks / KaijuOrgansの再生成 | — | 決定 | ▲ | - | 既存の4,687Partsと臓器マーカー6個は参照データ。タコ用に作り直す必要があるが行が無い
LOOP-01 | MVP | LOOP コアループ/ラン構造 | 解体率システム（総ブロック数 vs 残り、チーム共有値） | 3.1 / D3 | 決定 | ○ | A3
LOOP-02 | MVP | LOOP コアループ/ラン構造 | 解体率100％でのクリア判定 | 3.1 / D3 | 決定 | ○ | A3
LOOP-03 | MVP | LOOP コアループ/ラン構造 | クリア演出とリザルト画面 | 2 | 決定 | ▲ | - | 不足#1。大周期ループの尻尾が無い
LOOP-04 | MVP | LOOP コアループ/ラン構造 | 報酬の確定と持ち帰り（ラン終了→ロビー帰還） | 2 / 12 | 決定 | ▲ | - | 不足#1。GDD 2 の⑦「報酬を持ち帰る」⑧「ロビーで強化」。DoDは ends cleanly と書いているが作る行が無い
LOOP-05 | MVP | LOOP コアループ/ラン構造 | 体力システム（自然回復なし、0でラン終了） | 3.1 / D4 | 決定 | ○ | B3
LOOP-06 | MVP | LOOP コアループ/ラン構造 | 回復アイテム：ロビーから持ち込み | 3.1 / 8.2 / D4 | 決定 | ○ | A13
LOOP-07 | MVP | LOOP コアループ/ラン構造 | 回復アイテム：怪獣内部から発見 | 3.1 / D4 | 決定 | ○ | A13
LOOP-08 | MVP | LOOP コアループ/ラン構造 | 短周期ループの成立（削る→発見→身構える→対処→復帰） | 2.1 | 決定 | ○ | A12 / A16 | 本作の中心。実体はイベント側の頻度とテンポ
LOOP-09 | MVP | LOOP コアループ/ラン構造 | ソロでも怪獣の基本難易度を変えない | 3.1 / D2 | 決定 | ○ | B8
LOOP-10 | MVP | LOOP コアループ/ラン構造 | 難易度NORMALのみ実装 | 3.2 | 仮 | ○ | B10
LOOP-11 | 後 | LOOP コアループ/ラン構造 | HARD / EXTREMEの本調整（イベント頻度・同時発生数・敵の強さ・報酬倍率） | 3.2 | 仮 | × | CUT
LOOP-12 | MVP | LOOP コアループ/ラン構造 | 1プレイの目標時間を暫定で置いて計測する | 14 N1 | 未確定 | ○ | O-C | 暫定15分
LOOP-13 | 後 | LOOP コアループ/ラン構造 | 図版 FIG-11 難易度別のイベント密度 | 付録A | 未作成 | × | -
TOOL-01 | MVP | TOOL 装備/インベントリ | レーザーカッター：ブロックのみ切る、敵にダメージを与えない | 4.2 / D9 | 決定 | ○ | A5
TOOL-02 | MVP | TOOL 装備/インベントリ | 銃：弾数無制限、敵のみにダメージ、怪獣の通常部位は切らない | 4.2 / D8 / D9 | 決定 | ○ | A6
TOOL-03 | MVP | TOOL 装備/インベントリ | ガスマスク：毒ガスの継続ダメージを防ぐ | 4.1 / 6.1 / D5 | 決定 | ○ | A9
TOOL-04 | MVP | TOOL 装備/インベントリ | ガスマスク4段階のFOV（Lv1 狭い 〜 Lv4 100％） | 6.1 | 決定 | ○ | A9 | 安全と視界のトレードオフ。装備更新の価値を画面で実感させる
TOOL-05 | MVP | TOOL 装備/インベントリ | 4枠インベントリ、第4枠は空欄 | 4 / D5 | 決定 | ○ | B5
TOOL-06 | MVP | TOOL 装備/インベントリ | 装備切替は1アクションで完了 | 4.2 | 決定 | ○ | B5
TOOL-07 | MVP | TOOL 装備/インベントリ | 銃のラインアップ（ハンドガン → 強化ハンドガン → ショットガン → アサルトライフル） | 8.2 | 仮 | ▲ | - | 不足#5。A6は銃1種、B11は guns 複数。MVPで何丁出すかが未定義
TOOL-08 | 後 | TOOL 装備/インベントリ | 武器の用途差（単体火力・範囲・連射・ノックバック） | 8.2 | 仮 | ▲ | - | 不足#5。「単純な上位互換だけにすると選択が消える」
TOOL-09 | 後 | TOOL 装備/インベントリ | 第4スロットのロール専用アイテム | 4.1 / D5 | 決定 | × | CUT
TOOL-10 | 後 | TOOL 装備/インベントリ | レーザーライフル等のSF武器 | 8.2 | 仮 | × | -
DRN-01 | MVP | DRN ドローン | 補助ドローンの実装（タレットは廃止） | 5.1 / D6 | 決定 | ○ | A10
DRN-02 | MVP | DRN ドローン | 通常の肉・骨ブロックのみ破壊、イベントブロックには触れない | 5.2 / D7 | 決定 | ○ | A10 | SKIN/MEAT/BONE/ORGAN/EGGのマテリアル分離が既にあるので実装は軽い
DRN-03 | MVP | DRN ドローン | イベント部位に覆いかぶさる通常部位は削り、イベント部位だけを露出して残す | 5.3 | 決定 | ▲ | - | 不足#9。A10は never event blocks まで。埋まったイベントブロックの芯を残す隣接探索は別実装
DRN-04 | MVP | DRN ドローン | イベント発生権はプレイヤーのみに留める | 5.2 / 5.3 | 決定 | ○ | A10
DRN-05 | MVP | DRN ドローン | 寄与率の校正（強化後もプレイヤー本人の寄与を下回る） | 5.4 / 14 N4 | 要検証 | ○ | A11
DRN-06 | MVP | DRN ドローン | ドローンだけで放置クリアできる強さを禁止 | 5.2 | 決定 | ○ | A11
DRN-07 | 後 | DRN ドローン | ドローンの強化軸（速度・稼働時間・台数・探索範囲） | 8.1 | 仮 | × | CUT
DRN-08 | MVP | DRN ドローン | ドローンモデルの制作 | 5 | 決定 | ○ | M2c
DRN-09 | MVP | DRN ドローン | ドローンのアニメーション | 5 | 決定 | ○ | M1e
EVT-01 | MVP | EVT ランダムイベント | イベントブロックを怪獣内部に埋める | 6 | 決定 | ○ | A2 / A4
EVT-02 | MVP | EVT ランダムイベント | 発光・形状で「何かある」ことを示し、結果は壊すまで確定しない | 6 | 決定 | ○ | M2c
EVT-03 | MVP | EVT ランダムイベント | 毒ガス：臓器ブロック破壊で発生（StomachGasHazardを移植し任意の臓器へ再ターゲット） | 6.1 | 決定 | ○ | A8
EVT-04 | MVP | EVT ランダムイベント | 毒ガス：画面にガスが充満し視認性が低下する | 6.1 | 決定 | ▲ | - | 不足#4。A8は既存ハザードの移植、A9はマスクのFOV段階。スプシ§3も no FOV effect と書いている。M2cはイベントブロックVFXで別物
EVT-05 | MVP | EVT ランダムイベント | 毒ガス：未装着時は体力が継続減少、マスク装着で防止 | 6.1 | 決定 | ○ | A8 / A9
EVT-06 | MVP | EVT ランダムイベント | 卵：破壊で卵が割れ、幼生が出現して暴れる | 6.2 | 決定 | ○ | A7
EVT-07 | MVP | EVT ランダムイベント | 幼生：プレイヤーを追跡し、接触または固有攻撃でダメージ | 6.2 | 決定 | ○ | A7
EVT-08 | MVP | EVT ランダムイベント | 卵の大きさ・色・脈動で危険度を予告する | 6.2 | 仮 | ▲ | - | M2cは卵の脈動VFXまで。危険度との対応付けが無い
EVT-09 | 後 | EVT ランダムイベント | 低確率で希少報酬やペット候補が出る派生 | 6.2 | 仮 | × | -
EVT-10 | 後 | EVT ランダムイベント | 要救助者イベント（救助で即時報酬またはクリア後ボーナス、お礼を言って去る） | 6.3 | 決定 | × | CUT | 6.3「戦闘ではなく発見の喜びを作る当たりイベント」。EVT-18を参照
EVT-11 | 後 | EVT ランダムイベント | 要救助者に失敗条件（誤破壊・時間切れ）を設けるか | 6.3 / 14 N8 | 未確定 | × | -
EVT-12 | MVP | EVT ランダムイベント | UFOレーザー（予告ライン → 猶予 → 着弾、作業位置を強制的に変える） | 6.4 | 決定 | × | CUT / O-B | GDD ch.12はMVPに入れている。スプシは外しており、クライアント承認が必要
EVT-13 | MVP | EVT ランダムイベント | UFOを撃墜可能にするか、一定時間で去るか | 6.4 / 14 N7 | 未確定 | × | O-E
EVT-14 | 後 | EVT ランダムイベント | 宇宙人襲来（着陸・転送ビーム・ポータルから小型怪獣が複数出現） | 6.5 | 決定 | × | CUT
EVT-15 | MVP | EVT ランダムイベント | 抽選方針：直前に起きたイベントの連続抽選を抑制 | 6.6 | 決定 | ○ | A12
EVT-16 | MVP | EVT ランダムイベント | 抽選方針：低解体率帯は単発、高解体率帯は複合を許可 | 6.6 | 決定 | ○ | A12
EVT-17 | MVP | EVT ランダムイベント | 抽選方針：4人時は敵数を増やすが、イベント数の単純4倍化は避ける | 6.6 | 決定 | ▲ | - | 不足#11。A12は連続防止と低%帯の単発化のみ
EVT-18 | MVP | EVT ランダムイベント | 抽選方針：プラスイベントを混ぜ、危機だけが続かないようにする | 6.6 | 決定 | ▲ | - | 構造的な問題。MVPは毒ガスと幼生の2種で両方が危機。要救助者とUFOを外した結果、この原則を満たせない。中心仮説の指標K9の解釈に影響する
EVT-19 | 後 | EVT ランダムイベント | 初回プレイではイベント種類を絞り、理解後に解禁する | 6.6 | 未確定 | × | -
EVT-20 | MVP | EVT ランダムイベント | イベント抽選頻度と連続防止ルールの確定 | 14 N5 | 未確定 | ○ | A16
EVT-21 | 後 | EVT ランダムイベント | 怪獣固有イベントを1つ以上持たせる | 7.2 | 決定 | × | - | 怪獣1体・汎用2種のMVPでは該当なし
KJU-01 | MVP | KJU 怪獣 | 緑色の巨大タコ型をMVP怪獣として制作 | 7.1 / FIG-08 / 12 | 決定 | ○ | M1a / M1b / M1d
KJU-02 | MVP | KJU 怪獣 | SDFスケルトンをタコとして再オーサリング（触手を道と壁に） | 7.1 | 決定 | ○ | A4
KJU-03 | MVP | KJU 怪獣 | 発注条件①：登り口が最低2箇所 | 7.1 | 決定 | ○ | M1a
KJU-04 | MVP | KJU 怪獣 | 発注条件②：内部へ入る開口（口・傷口・裂け目） | 7.1 | 決定 | ○ | M1a
KJU-05 | MVP | KJU 怪獣 | 発注条件③：イベントブロックを埋める体積の確保 | 7.1 | 決定 | ▲ | - | 不足#10。M1aは①②のみ、B6の検証も climb routes と interior access まで
KJU-06 | MVP | KJU 怪獣 | 登りルートと内部アクセスの実機検証 | 7.1 | 決定 | ○ | B6
KJU-07 | MVP | KJU 怪獣 | 解体ブロック数と怪獣体積の確定（N1から逆算） | 14 N3 | 未確定 | ○ | O-C
KJU-08 | MVP | KJU 怪獣 | ブロック数のスケール検証（4人で1体に集まった時の複製負荷） | — | 要検証 | ○ | §9 / Day5 | 4,687Partsは1人分。lazy revealが71%削っている
KJU-09 | 後 | KJU 怪獣 | 怪獣2体目：二足歩行する巨大深海魚型 | 7.1 / FIG-09 | 決定 | × | CUT
KJU-10 | 後 | KJU 怪獣 | 怪獣3体目：巨大人型宇宙人 | 7.1 / FIG-10 | 決定 | × | CUT
KJU-11 | 後 | KJU 怪獣 | 10人規模の超巨大怪獣レイド | 7.2 | 決定 | × | -
KJU-12 | MVP | KJU 怪獣 | ブロック破壊パーティクルとLOD | — | 決定 | ○ | M1d
PRG-01 | MVP | PRG 成長/ショップ | 強化軸：解体（カッターの削る速度・範囲） | 8.1 | 決定 | ○ | A14
PRG-02 | MVP | PRG 成長/ショップ | 強化軸：ドローン | 8.1 | 決定 | × | CUT | GDD ch.12は3軸すべてをMVPに入れている
PRG-03 | MVP | PRG 成長/ショップ | 強化軸：戦闘（銃の攻撃力・連射・範囲） | 8.1 | 決定 | × | CUT | GDD ch.12は3軸すべてをMVPに入れている
PRG-04 | MVP | PRG 成長/ショップ | 購入の永続化 | 8 | 決定 | ○ | A14
PRG-05 | MVP | PRG 成長/ショップ | ショップ：ガスマスク4段階 | 8.2 / 11.1 | 決定 | ○ | B11
PRG-06 | MVP | PRG 成長/ショップ | ショップ：銃 | 8.2 / 11.1 | 決定 | ○ | B11
PRG-07 | MVP | PRG 成長/ショップ | ショップ：回復アイテム | 8.2 / 11.1 | 決定 | ○ | B11
PRG-08 | MVP | PRG 成長/ショップ | ショップ：防護服の色替え・外見カスタマイズ | 8.2 / 11.1 | 決定 | ▲ | - | 誤読。スプシ§6が11.2の継続施策として延期しているが、GDD 11.1「初期に必要」かつ8.2のショップ商品。章の取り違え
PRG-09 | 後 | PRG 成長/ショップ | 難易度別の報酬倍率 | 3.2 / 14 N9 | 未確定 | × | - | NORMALのみなので該当なし
HUD-01 | MVP | HUD 画面/カメラ | 画面上部：チーム共通の解体率 | 9.1 | 決定 | ○ | B9
HUD-02 | MVP | HUD 画面/カメラ | 画面左下：体力 | 9.1 | 決定 | ○ | B9
HUD-03 | MVP | HUD 画面/カメラ | 画面下部：4枠インベントリ | 9.1 | 決定 | ○ | B9
HUD-04 | MVP | HUD 画面/カメラ | 画面端：現在のイベント警告 | 9.1 | 決定 | ○ | B9
HUD-05 | MVP | HUD 画面/カメラ | 画面右側：ドローンカメラ切替ボタン | 9.1 | 決定 | × | CUT | 不足#12。ドローンカメラCUTに連動して省略。9.1からの意図的な逸脱として明記が必要
HUD-06 | MVP | HUD 画面/カメラ | 図版 FIG-12 HUDモック（解体率・体力・4枠・警告） | 付録A / 9.1 | 未作成 | ▲ | - | 不足#8。B9のHUD実装がDay5、M2fのUIアートがDay6。モックが無い状態でHUDを組む順序になっている
HUD-07 | MVP | HUD 画面/カメラ | HUDアート（フレーム・アイコン・警告グラフィック） | 9.1 | 決定 | ○ | M2f
HUD-08 | MVP | HUD 画面/カメラ | ドローンカメラ（鳥瞰・短時間ビュー・操作可能なまま） | 9.2 | 決定 | × | CUT | K6ゲート。最後の1%探しが実測で悪ければ作る
HUD-09 | MVP | HUD 画面/カメラ | 未解体部位の色ハイライト | 9.2 | 未確定 | × | CUT | K6ゲート
HUD-10 | 後 | HUD 画面/カメラ | 図版 FIG-13 ドローンカメラのハイライト | 付録A | 未作成 | × | -
MAP-01 | MVP | MAP マップ/導入 | 壊れた海辺の都市のグレーボックス（スポーン・出動地点） | 10.1 / 12 | 決定 | ○ | B1
MAP-02 | MVP | MAP マップ/導入 | 海辺の街・港湾キット（建物・ドック・クレーン・瓦礫） | 10.1 | 決定 | ○ | M2b
MAP-03 | MVP | MAP マップ/導入 | ドレッシングパス1〜3と怪獣の配置 | 10.1 | 決定 | ○ | B4 / B6 / M2e
MAP-04 | MVP | MAP マップ/導入 | ライティングとスカイボックス | 10.1 | 決定 | ○ | M2e
MAP-05 | MVP | MAP マップ/導入 | トーン指定：恐怖よりも「巨大災害の後始末をする作業現場」 | 10.1 | 方針 | ▲ | - | 不足#14。アート発注の指針としてどこにも書かれていない
MAP-06 | 後 | MAP マップ/導入 | 崩壊した都市中心部（別マップ） | 10.1 | 決定 | × | -
MAP-07 | 後 | MAP マップ/導入 | 砂漠基地・雪原研究所・海上施設 | 10.1 | 決定 | × | -
MAP-08 | MVP | MAP マップ/導入 | 冒頭ムービー（戦闘跡 → 倒れた怪獣 → 処理班到着 → 任務提示） | 10.2 | 決定 | × | CUT
MAP-09 | MVP | MAP マップ/導入 | テキスト任務ブリーフ（冒頭ムービーの代替） | 10.2 | 決定 | ○ | B13
MAP-10 | MVP | MAP マップ/導入 | 初回は説明付き、2回目以降はスキップ可能 | 10.2 | 決定 | ▲ | - | 不足#13。B13はテキストブリーフのみ、スキップ制御が無い
LBY-01 | MVP | LBY ロビー | 出動口・怪獣選択 | 11.1 | 決定 | ○ | B10
LBY-02 | MVP | LBY ロビー | 難易度選択（NORMALのみ） | 11.1 | 決定 | ○ | B10
LBY-03 | MVP | LBY ロビー | アイテムショップ | 11.1 | 決定 | ○ | B11
LBY-04 | MVP | LBY ロビー | 装備・スキル強化 | 11.1 | 決定 | ○ | A14
LBY-05 | MVP | LBY ロビー | ロビー環境・ショップ屋台・出動ゲートのモデル | 11.1 | 決定 | ○ | M2d
LBY-06 | 後 | LBY ロビー | 7日ログインボーナス | 11.2 | 決定 | × | CUT
LBY-07 | 後 | LBY ロビー | デイリークエスト（500ブロック解体／救助2人／幼生10体／ノーダウンでガス／HARD1回） | 11.2 | 決定 | × | CUT
LBY-08 | 後 | LBY ロビー | 怪獣図鑑 | 11.2 | 決定 | × | CUT
LBY-09 | 後 | LBY ロビー | 記録（救助人数・討伐数・解体量） | 11.2 | 決定 | × | CUT
COOP-01 | MVP | COOP 協力/ネットワーク | ブロック破壊を4クライアントへ複製（ネットワーキングスパイク） | D2 | 決定 | ○ | B7 | スプシ§9の最大リスク。プロトタイプは一切マルチプレイでない
COOP-02 | MVP | COOP 協力/ネットワーク | 1〜4人協力：解体率の共有・プレイヤーリスト・参加/離脱 | 3.1 / D2 | 決定 | ○ | B8
COOP-03 | MVP | COOP 協力/ネットワーク | プレイヤー死亡時の処理（復帰・観戦） | 14 N6 | 未確定 | ▲ | O-D | 不足#3。O-Dで「Day5のco-op作業前に必要」と旗は立つが、4人中1人が死んだらどうなるかを作る行が無い
COOP-04 | MVP | COOP 協力/ネットワーク | 全滅条件とラン終了処理 | 14 N6 | 未確定 | ▲ | O-D | 不足#3
COOP-05 | MVP | COOP 協力/ネットワーク | 4人時の複製負荷測定 | — | 要検証 | ○ | §9 / Day5
ECO-01 | MVP | ECO 経済/報酬 | ラン内通貨と恒久通貨の実装 | 14 N10 | 未確定 | ▲ | - | 不足#2。分離方式はRES-10で決定。B11（ショップ）とA14（強化購入）は何を払うのか決まらないと作れない
ECO-02 | MVP | ECO 経済/報酬 | 報酬テーブル（クリア報酬・イベント報酬） | 2 / 12 | 未確定 | ▲ | - | 不足#1 / #2
ECO-03 | MVP | ECO 経済/報酬 | 強化コストと報酬のバランス | 8 / 14 N10 | 未確定 | ▲ | -
ECO-04 | MVP | ECO 経済/報酬 | ショップ価格（マスク4段階・銃・回復アイテム） | 8.2 | 仮 | ▲ | -
ART-01 | MVP | ART アート/LD | 防護服・レーザーカッター・銃・ガスマスクのモデル | 4.1 | 決定 | ○ | M2a
ART-02 | MVP | ART アート/LD | 幼生クリーチャーとアニメーション | 6.2 | 決定 | ○ | M1c
ART-03 | MVP | ART アート/LD | イベントブロックVFX（臓器の発光・卵の脈動） | 5 / 6 | 決定 | ○ | M2c
ART-04 | MVP | ART アート/LD | 既存作品を想起させないオリジナルデザインの徹底（怪獣・宇宙人・UFO・防護服） | 付録A ⚠ / 7.1 | 方針 | ▲ | - | 不足#6。タスク行が無い。sneakers側で著作権リグ60体が公開ブロッカーになっている前例がある
ART-05 | MVP | ART アート/LD | タコのオーサリング難度対策（触手はSDFで表現しづらい） | 7.1 | 要検証 | ○ | §9 | 1.5日見積。フォールバックは既存の四足形状をリスキン
RES-01 | — | RES 調査/検証 | N1 1プレイの目標時間を決める | 14 N1 | 未確定 | ○ | O-C
RES-02 | — | RES 調査/検証 | N2 ソロと4人の平均クリア時間許容差を決める | 14 N2 / 3.2 | 未確定 | ▲ | - | 不足#7。GDD 3.2【要検証】が名指しし、K2で計測はするが、判断項目として立っていない。D2（ソロでも難易度を変えない）の妥当性を決める唯一の論点
RES-03 | — | RES 調査/検証 | N3 解体ブロック数と怪獣体積を決める | 14 N3 | 未確定 | ○ | O-C
RES-04 | — | RES 調査/検証 | N4 ドローンの寄与率上限を決める | 14 N4 | 未確定 | ○ | A11
RES-05 | — | RES 調査/検証 | N5 イベント抽選頻度と連続防止ルールを決める | 14 N5 | 未確定 | ○ | A12 / A16
RES-06 | — | RES 調査/検証 | N6 死亡時の復帰・観戦・全滅条件を決める | 14 N6 | 未確定 | ○ | O-D | Day5のco-op作業前に回答が必要
RES-07 | — | RES 調査/検証 | N7 UFOを撃墜できるか決める | 14 N7 | 未確定 | × | O-E | O-Bに従属
RES-08 | — | RES 調査/検証 | N8 要救助者に失敗条件を設けるか決める | 14 N8 | 未確定 | × | -
RES-09 | — | RES 調査/検証 | N9 難易度別の報酬倍率を決める | 14 N9 | 未確定 | × | -
RES-10 | — | RES 調査/検証 | N10 1ラン中の収入と恒久通貨の分離を決める | 14 N10 | 未確定 | ▲ | - | 不足#2。OPEN ITEMSに無いのに、Day6のB11とA14がこれに依存している
RES-11 | — | RES 調査/検証 | UFOイベントをMVPから外すことのクライアント承認 | 6.4 / 12 | 未確定 | ○ | O-B | GDD ch.12はMVPに入れている。Day3までに回答が必要
RES-12 | — | RES 調査/検証 | 専任チーム構成の確定 | — | 未確定 | ○ | O-A | 2026-09-19にクローズ
KPI-01 | MVP | KPI 計測 | K1 1プレイ完走率 | 15 K1 | 決定 | ○ | A15
KPI-02 | MVP | KPI 計測 | K2 平均クリア時間と人数別クリア時間 | 15 K2 | 決定 | ○ | A15
KPI-03 | MVP | KPI 計測 | K3 解体作業時間とイベント対応時間の比率 | 15 K3 | 決定 | ○ | A15 | 中心仮説
KPI-04 | MVP | KPI 計測 | K4 イベント発生後に解体へ戻るまでの時間 | 15 K4 | 決定 | ○ | A15 | 中心仮説。短周期ループが閉じているか
KPI-05 | MVP | KPI 計測 | K5 ドローンによる解体寄与率 | 15 K5 | 決定 | ○ | A15
KPI-06 | MVP | KPI 計測 | K6 99％以降に残り部位を探す時間 | 15 K6 | 決定 | ○ | A15 | ドローンカメラの要否を決める
KPI-07 | MVP | KPI 計測 | K7 装備切替ミスによる被ダメージ | 15 K7 | 決定 | ○ | A15
KPI-08 | MVP | KPI 計測 | K8 ソロと協力時のダウン率 | 15 K8 | 決定 | ○ | A15
KPI-09 | MVP | KPI 計測 | K9 同一怪獣の再プレイ率 | 15 K9 | 決定 | ○ | A15 | 本作の中心仮説。EVT-18（当たりイベント不在）の影響を受けるので、解釈に留保が必要
KPI-10 | MVP | KPI 計測 | 構造化イベントログの基盤 | 15 | 決定 | ○ | A15
KPI-11 | MVP | KPI 計測 | 実ランからK1〜K9が出ていることの確認 | 15 | 決定 | ○ | B15
REL-01 | MVP | REL リリース/QA | フルQAパス（ソロと4人・両イベント・ドローン規則・武器分離） | — | 決定 | ○ | B12
REL-02 | MVP | REL リリース/QA | D7検証：ドローンがイベントブロックを壊さない | D7 | 決定 | ○ | A18
REL-03 | MVP | REL リリース/QA | D9検証：カッターは敵に無効、銃は怪獣を切らない | D9 | 決定 | ○ | A18
REL-04 | MVP | REL リリース/QA | バランス調整（削る速度・イベント頻度・幼生の強さ） | 14 N1 / N5 | 仮 | ○ | A16
REL-05 | MVP | REL リリース/QA | QAからのバグ修正 | — | 決定 | ○ | A17
REL-06 | MVP | REL リリース/QA | 公開設定・プレイス設定 | — | 決定 | ○ | B14
REL-07 | MVP | REL リリース/QA | DoD：1〜4人のランが100％に到達し、きれいに終わる | — | 決定 | ○ | B12 | LOOP-03 / LOOP-04 が無いと満たせない
REL-08 | MVP | REL リリース/QA | Dev A Day4の12h超過の解消 | — | 未確定 | ▲ | - | 工数検算。A8 3h + A9 4h + A10 5h。Day5のDev Aは6hなのでA10かA9を移す。Day2とDay3も9h
REL-09 | MVP | REL リリース/QA | A7（Day3）が同日のM1c（Day3）に依存している同日依存の解消 | — | 未確定 | ▲ | - | 工数検算。M1cの8hが終わるまでA7の5hは始められず、実質Day4へ押し出される
REL-10 | MVP | REL リリース/QA | スプシ§6の章取り違えの修正（防護服の色替え） | 11.1 / 11.2 | 決定 | ▲ | - | 誤読。11.2の継続施策に入れているが、GDD 11.1「初期に必要」
REL-11 | MVP | REL リリース/QA | HUD 9.1からの逸脱（ドローンカメラ切替ボタン省略）の明記 | 9.1 | 決定 | ▲ | -

## Spec Gaps
# | 種別 | 項目 | 出所 | 現状 | 影響 | 全リストID
G01 | 不足 | クリア処理〜報酬〜ロビー帰還 | GDD 2 ⑦⑧ / 12 | A3は解体率の計算まで。クリア演出・リザルト・報酬確定・ロビー帰還の行が無い | 大周期ループの尻尾が欠けている。DoDの ends cleanly を満たせない | LOOP-03 / LOOP-04 / ECO-02
G02 | 不足 | 通貨・報酬設計 | GDD 14 N10 | N10がOPEN ITEMSにも無い | B11（ショップ）とA14（強化購入の永続化）は何を払うのか決まらないと作れない。Day6の2タスクが宙に浮く | ECO-01 to ECO-04 / RES-10
G03 | 不足 | 協力時の死亡・観戦・全滅処理の実装 | GDD 3.1 / 14 N6 | O-Dで旗は立つが、B8は共有%・プレイヤーリスト・参加離脱のみ | 4人中1人が死んだらどうなるかを作る行が無い。Day5のco-op作業の前提 | COOP-03 / COOP-04 / RES-06
G04 | 不足 | 毒ガス自体の視界低下 | GDD 6.1 | A8は既存ハザードの移植、A9はマスクのFOV段階。スプシ§3も no tiers or FOV effect と書いている | 6.1の「画面にガスが充満して視認性が低下する」を作る行が無い。M2cはイベントブロックVFXで別物 | EVT-04
G05 | 不足 | 銃のラインアップと用途差 | GDD 8.2 | A6は銃1種、B11は guns 複数 | MVPで何丁出すかが未定義。用途差（単体火力・範囲・連射・ノックバック）も未着手 | TOOL-07 / TOOL-08
G06 | 不足 | オリジナリティ確認 | GDD 付録A ⚠ / 7.1 | タスク行が無い | 怪獣・宇宙人・UFO・防護服のすべてが対象。sneakers側で著作権リグ60体が公開ブロッカーになっている前例がある | ART-04
G07 | 不足 | N2 ソロと4人のクリア時間許容差 | GDD 3.2 / 14 N2 | OPEN ITEMSに無い。K2で計測はする | GDD 3.2【要検証】が名指しした論点。D2（ソロでも難易度を変えない）の妥当性を決める唯一の判断材料 | RES-02
G08 | 不足 | FIG-12 HUDモックが未作成のまま実装が先行 | GDD 付録A / 9.1 | 図版は未作成 | B9（HUD実装）がDay5、M2f（UIアート）がDay6。モックが無い状態でHUDを組む順序になっている | HUD-06
G09 | 不足 | ドローンが埋まったイベントブロックの周囲だけ削る挙動 | GDD 5.3 | A10は never event blocks まで | 「周囲の通常部位まで削り、イベント部位だけを露出したまま残す」は隣接探索の別実装。D7の一番細かい部分 | DRN-03
G10 | 不足 | 怪獣発注の3条件のうち③ イベントブロックを埋める体積 | GDD 7.1 | M1aは①登り口2箇所と②口の開口のみ | B6の検証も climb routes と interior access まで。体積の確認が抜けている | KJU-05
G11 | 不足 | イベント抽選の人数補正 | GDD 6.6 | A12は連続防止と低%帯の単発化のみ | 「4人時は敵数を増やしてもよいが、イベント数の単純4倍化は避ける」が落ちている | EVT-17
G12 | 不足 | HUD 9.1のドローンカメラ切替ボタン | GDD 9.1 | B9の記述から省略されている | ドローンカメラCUTに連動した省略だとしても、9.1からの逸脱として明記すべき | HUD-05 / REL-11
G13 | 不足 | 導入の初回説明とスキップ制御 | GDD 10.2 | B13はテキストブリーフのみ | 「初回は説明付き、2回目以降スキップ可能」の制御が無い | MAP-10
G14 | 不足 | マップのトーン指定 | GDD 10.1 | どこにも書かれていない | 「恐怖よりも巨大災害の後始末をする作業現場」がアート発注の指針として渡っていない | MAP-05
M01 | 誤読 | 防護服の色替えの章取り違え | GDD 11.1 vs 11.2 | スプシ§6が 11.2 の継続施策として延期している | 色替えは 11.1「初期に必要」に入っており、8.2 でもショップ商品として扱われている。11.2 は7日ログイン・デイリー・図鑑・記録の4件。工数は小さいのでB11に一行足せば解消 | PRG-08 / REL-10
S01 | 工数 | Dev A の日次工数が8hを超えている | — | Day2 9h / Day3 9h / Day4 12h / Dev B Day5 10h。Dev A 合計67h | Day4はA8 3h + A9 4h + A10 5h。しかも同じ日がco-opのGO/NO-GO判定日で、Dev BがB7スパイク6hを走らせている。Day5のDev Aは6hなのでA10かA9を移せる | REL-08
S02 | 工数 | A7 が同日の M1c に依存している | — | A7（卵イベント・Day3・5h）が M1c（幼生モデル・Day3・8h）に依存 | M1cの8hが終わるまでA7は始められず、実質Day4へ押し出される。Day4はすでに12h | REL-09
D01 | 論点 | MVPの2イベントが両方とも「危機」 | GDD 6.6 / 6.3 / 15 K9 | 毒ガスと幼生の2種。要救助者（6.3）とUFO（6.4）は両方CUT | 6.6は「救助などのプラスイベントを混ぜ、危機だけが続かないようにする」と明記しており、MVPは構造上これを満たせない。中心仮説の指標はK9（同一怪獣の再プレイ率）なので、当たりイベントが1つも無い状態で測ると仮説ではなく危機だけの構成を測ることになる。要救助者は戦闘なし・お礼を言って去るだけで失敗条件も未確定（N8）なので実装は軽く、幼生（A7 5h + M1c 8h + 追跡AI）より安い可能性がある | EVT-18 / EVT-10 / KPI-09

## All Tasks (EN)
ID | Phase | Group | Task | Spec | Status | MVP | MVP task | Note
SET-01 | - | SET Setup & Port | Create the KAITAI place, folder structure and a server-authoritative layout | — | Decided | In | A1
SET-02 | - | SET Setup & Port | Port KaijuBlockBuilder out of the pirate place and verify lazy reveal and BreakAt | 1.1 | Decided | In | A2 | 16,251 cells with only 29% spawned as Parts. The hardest single piece, reused
SET-03 | - | SET Setup & Port | Config modules: KaijuConfig, ToolConfig, EventConfig, DroneConfig | — | Decided | In | B2
SET-04 | - | SET Setup & Port | Drive every value from Config | 0 | Provisional | In | B2 | Nearly every GDD number is provisional and settles on the Ch. 15 measurements
SET-05 | - | SET Setup & Port | Regenerate KaijuBlocks and KaijuOrgans | — | Decided | Gap | - | The existing 4,687 Parts and 6 organ markers are reference data only; they must be regenerated for the octopus and no row covers it
LOOP-01 | MVP | LOOP Core Loop & Run | Demolition percentage: total versus remaining blocks, as a shared team value | 3.1 / D3 | Decided | In | A3
LOOP-02 | MVP | LOOP Core Loop & Run | Clear check at 100% demolition | 3.1 / D3 | Decided | In | A3
LOOP-03 | MVP | LOOP Core Loop & Run | Clear sequence and the result screen | 2 | Decided | Gap | - | Gap #1. The tail of the long loop is missing
LOOP-04 | MVP | LOOP Core Loop & Run | Settle the rewards and carry them home: end of run back to the lobby | 2 / 12 | Decided | Gap | - | Gap #1. GDD 2 steps 7 and 8. The definition of done says ends cleanly, but no row builds it
LOOP-05 | MVP | LOOP Core Loop & Run | HP system: no passive regeneration, zero ends the run | 3.1 / D4 | Decided | In | B3
LOOP-06 | MVP | LOOP Core Loop & Run | Healing items brought from the lobby | 3.1 / 8.2 / D4 | Decided | In | A13
LOOP-07 | MVP | LOOP Core Loop & Run | Healing items found inside the kaiju | 3.1 / D4 | Decided | In | A13
LOOP-08 | MVP | LOOP Core Loop & Run | Close the short loop: cut, spot, brace, deal with it, back to work | 2.1 | Decided | In | A12 / A16 | The heart of the game; it lives in event frequency and pacing
LOOP-09 | MVP | LOOP Core Loop & Run | The kaiju base difficulty never scales for solo | 3.1 / D2 | Decided | In | B8
LOOP-10 | MVP | LOOP Core Loop & Run | Ship NORMAL difficulty only | 3.2 | Provisional | In | B10
LOOP-11 | Post-launch | LOOP Core Loop & Run | Full HARD / EXTREME tuning: event frequency, overlap, enemy strength, reward multiplier | 3.2 | Provisional | Deferred | CUT
LOOP-12 | MVP | LOOP Core Loop & Run | Pick a provisional run length and measure against it | 14 N1 | Pending | In | O-C | Provisionally 15 minutes
LOOP-13 | Post-launch | LOOP Core Loop & Run | Figure FIG-11: event density by difficulty | 付録A | Not drawn | Deferred | -
TOOL-01 | MVP | TOOL Gear & Inventory | Laser cutter: cuts blocks only, does no damage to enemies | 4.2 / D9 | Decided | In | A5
TOOL-02 | MVP | TOOL Gear & Inventory | Gun: unlimited ammo, damages enemies only, never cuts the kaiju | 4.2 / D8 / D9 | Decided | In | A6
TOOL-03 | MVP | TOOL Gear & Inventory | Gas mask: blocks damage over time from toxic gas | 4.1 / 6.1 / D5 | Decided | In | A9
TOOL-04 | MVP | TOOL Gear & Inventory | Four gas-mask tiers by field of view, from narrow at Lv1 to full at Lv4 | 6.1 | Decided | In | A9 | Safety traded against sight, so an upgrade is visible on screen
TOOL-05 | MVP | TOOL Gear & Inventory | Four inventory slots with slot 4 left empty | 4 / D5 | Decided | In | B5
TOOL-06 | MVP | TOOL Gear & Inventory | Switching tools costs exactly one action | 4.2 | Decided | In | B5
TOOL-07 | MVP | TOOL Gear & Inventory | Gun line-up: handgun, upgraded handgun, shotgun, assault rifle | 8.2 | Provisional | Gap | - | Gap #5. A6 builds one gun while B11 sells guns plural; how many ship is undefined
TOOL-08 | Post-launch | TOOL Gear & Inventory | Differentiate weapons by single-target damage, area, rate of fire and knockback | 8.2 | Provisional | Gap | - | Gap #5. If every weapon is strictly better, there is no choice left
TOOL-09 | Post-launch | TOOL Gear & Inventory | The role item for slot 4 | 4.1 / D5 | Decided | Deferred | CUT
TOOL-10 | Post-launch | TOOL Gear & Inventory | Sci-fi weapons such as a laser rifle | 8.2 | Provisional | Deferred | -
DRN-01 | MVP | DRN Support Drone | Support drone; turrets are dropped | 5.1 / D6 | Decided | In | A10
DRN-02 | MVP | DRN Support Drone | Destroys ordinary flesh and bone only, never event blocks | 5.2 / D7 | Decided | In | A10 | The existing SKIN/MEAT/BONE/ORGAN/EGG material split makes this cheap
DRN-03 | MVP | DRN Support Drone | Clear the ordinary blocks covering an event block and leave the event block standing | 5.3 | Decided | Gap | - | Gap #9. A10 stops at never event blocks; peeling around a buried block is separate adjacency work
DRN-04 | MVP | DRN Support Drone | Keep the decision to trigger an event with the player | 5.2 / 5.3 | Decided | In | A10
DRN-05 | MVP | DRN Support Drone | Calibrate the drone share so even a fully upgraded drone contributes less than the player | 5.4 / 14 N4 | Verify | In | A11
DRN-06 | MVP | DRN Support Drone | Forbid any strength at which the drone could clear a run unattended | 5.2 | Decided | In | A11
DRN-07 | Post-launch | DRN Support Drone | Drone upgrade axis: speed, uptime, count, search radius | 8.1 | Provisional | Deferred | CUT
DRN-08 | MVP | DRN Support Drone | Support drone model | 5 | Decided | In | M2c
DRN-09 | MVP | DRN Support Drone | Drone animation | 5 | Decided | In | M1e
EVT-01 | MVP | EVT Random Events | Bury event blocks inside the kaiju | 6 | Decided | In | A2 / A4
EVT-02 | MVP | EVT Random Events | Shape and glow say something is there; the outcome is not fixed until the block breaks | 6 | Decided | In | M2c
EVT-03 | MVP | EVT Random Events | Toxic gas on breaking an organ block: port StomachGasHazard and retarget it to any organ | 6.1 | Decided | In | A8
EVT-04 | MVP | EVT Random Events | Toxic gas fills the screen and cuts visibility | 6.1 | Decided | Gap | - | Gap #4. A8 ports the hazard and A9 does mask FOV; the sheet's own audit says no FOV effect. M2c is event-block VFX, not this
EVT-05 | MVP | EVT Random Events | Without the mask HP drains continuously; with it the damage is blocked | 6.1 | Decided | In | A8 / A9
EVT-06 | MVP | EVT Random Events | Egg: breaking it cracks the shell and a larva emerges and rampages | 6.2 | Decided | In | A7
EVT-07 | MVP | EVT Random Events | Larva: chases players and damages them on contact or with its own attack | 6.2 | Decided | In | A7
EVT-08 | MVP | EVT Random Events | Foreshadow danger through egg size, colour and pulsing | 6.2 | Provisional | Gap | - | M2c covers the pulse VFX but nothing maps it to actual danger
EVT-09 | Post-launch | EVT Random Events | A rare variant dropping a prize or a pet candidate | 6.2 | Provisional | Deferred | -
EVT-10 | Post-launch | EVT Random Events | Survivor event: rescuing pays out immediately or after the clear, and the survivor thanks the player and leaves | 6.3 | Decided | Deferred | CUT | 6.3 calls it the jackpot event, where the pleasure is discovery not combat. See EVT-18
EVT-11 | Post-launch | EVT Random Events | Whether a rescue can fail through accidental destruction or a timer | 6.3 / 14 N8 | Pending | Deferred | -
EVT-12 | MVP | EVT Random Events | UFO laser: telegraph line, grace period, impact, forcing players to move | 6.4 | Decided | Deferred | CUT / O-B | GDD ch.12 puts this in the MVP. The sheet cuts it, so it needs client sign-off
EVT-13 | MVP | EVT Random Events | Whether the UFO can be shot down or simply leaves | 6.4 / 14 N7 | Pending | Deferred | O-E
EVT-14 | Post-launch | EVT Random Events | Alien invasion: a landing, a beam or a portal spills out several small kaiju | 6.5 | Decided | Deferred | CUT
EVT-15 | MVP | EVT Random Events | Roll policy: suppress an immediate repeat of the event that just fired | 6.6 | Decided | In | A12
EVT-16 | MVP | EVT Random Events | Roll policy: single events early in a run, compound events as demolition climbs | 6.6 | Decided | In | A12
EVT-17 | MVP | EVT Random Events | Roll policy: more enemies at four players, but never four times the events | 6.6 | Decided | Gap | - | Gap #11. A12 covers anti-repeat and single events at low percentages only
EVT-18 | MVP | EVT Random Events | Roll policy: mix in positive events so it is not crisis after crisis | 6.6 | Decided | Gap | - | A structural problem. The MVP has only gas and larvae, both crises. With survivors and the UFO cut, this principle cannot be met, which colours how K9 can be read
EVT-19 | Post-launch | EVT Random Events | Limit the event pool on a first run and open it once understood | 6.6 | Pending | Deferred | -
EVT-20 | MVP | EVT Random Events | Settle event frequency and the anti-repeat rules | 14 N5 | Pending | In | A16
EVT-21 | Post-launch | EVT Random Events | Give every kaiju at least one event unique to it | 7.2 | Decided | Deferred | - | Not applicable with one kaiju and two generic events
KJU-01 | MVP | KJU Kaiju | Model the green octopus as the MVP kaiju | 7.1 / FIG-08 / 12 | Decided | In | M1a / M1b / M1d
KJU-02 | MVP | KJU Kaiju | Re-author the SDF skeleton as the octopus, with tentacles as both paths and walls | 7.1 | Decided | In | A4
KJU-03 | MVP | KJU Kaiju | Art brief condition 1: at least two ways to climb on | 7.1 | Decided | In | M1a
KJU-04 | MVP | KJU Kaiju | Art brief condition 2: an opening into the interior — mouth, wound or split | 7.1 | Decided | In | M1a
KJU-05 | MVP | KJU Kaiju | Art brief condition 3: enough volume to bury event blocks in | 7.1 | Decided | Gap | - | Gap #10. M1a covers conditions 1 and 2, and B6 verifies climb routes and interior access only
KJU-06 | MVP | KJU Kaiju | Verify climb routes and interior access in engine | 7.1 | Decided | In | B6
KJU-07 | MVP | KJU Kaiju | Settle block count and kaiju volume, derived from N1 | 14 N3 | Pending | In | O-C
KJU-08 | MVP | KJU Kaiju | Measure block count at scale: replication load with four players on one kaiju | — | Verify | In | §9 / Day5 | 4,687 Parts is the single-player figure; lazy reveal already cuts 71%
KJU-09 | Post-launch | KJU Kaiju | Kaiju 2: the bipedal deep-sea fish | 7.1 / FIG-09 | Decided | Deferred | CUT
KJU-10 | Post-launch | KJU Kaiju | Kaiju 3: the giant humanoid alien | 7.1 / FIG-10 | Decided | Deferred | CUT
KJU-11 | Post-launch | KJU Kaiju | A 10-player raid on a colossal kaiju | 7.2 | Decided | Deferred | -
KJU-12 | MVP | KJU Kaiju | Block-break particles and LODs | — | Decided | In | M1d
PRG-01 | MVP | PRG Progression & Shop | Upgrade axis: demolition — cutter speed and area | 8.1 | Decided | In | A14
PRG-02 | MVP | PRG Progression & Shop | Upgrade axis: drone | 8.1 | Decided | Deferred | CUT | GDD ch.12 puts all three axes in the MVP
PRG-03 | MVP | PRG Progression & Shop | Upgrade axis: combat — gun damage, rate of fire, area | 8.1 | Decided | Deferred | CUT | GDD ch.12 puts all three axes in the MVP
PRG-04 | MVP | PRG Progression & Shop | Persist purchases across runs | 8 | Decided | In | A14
PRG-05 | MVP | PRG Progression & Shop | Shop: the four gas-mask tiers | 8.2 / 11.1 | Decided | In | B11
PRG-06 | MVP | PRG Progression & Shop | Shop: guns | 8.2 / 11.1 | Decided | In | B11
PRG-07 | MVP | PRG Progression & Shop | Shop: healing items | 8.2 / 11.1 | Decided | In | B11
PRG-08 | MVP | PRG Progression & Shop | Shop: suit recolouring and appearance customisation | 8.2 / 11.1 | Decided | Gap | - | Misread. The sheet defers this as an 11.2 retention feature, but GDD 11.1 lists it as required at launch and 8.2 sells it in the shop
PRG-09 | Post-launch | PRG Progression & Shop | Reward multipliers by difficulty | 3.2 / 14 N9 | Pending | Deferred | - | Not applicable with NORMAL only
HUD-01 | MVP | HUD Screen & Camera | Top of screen: the team's shared demolition percentage | 9.1 | Decided | In | B9
HUD-02 | MVP | HUD Screen & Camera | Bottom left: health | 9.1 | Decided | In | B9
HUD-03 | MVP | HUD Screen & Camera | Bottom: the four inventory slots | 9.1 | Decided | In | B9
HUD-04 | MVP | HUD Screen & Camera | Edges: active event warnings | 9.1 | Decided | In | B9
HUD-05 | MVP | HUD Screen & Camera | Right side: the drone camera toggle | 9.1 | Decided | Deferred | CUT | Gap #12. Omitted along with the drone camera. Should be recorded as a deliberate deviation from 9.1
HUD-06 | MVP | HUD Screen & Camera | Figure FIG-12: HUD mock with demolition percentage, health, four slots and warnings | 付録A / 9.1 | Not drawn | Gap | - | Gap #8. B9 builds the HUD on day 5 while M2f does the UI art on day 6, so the HUD is built before its mock exists
HUD-07 | MVP | HUD Screen & Camera | HUD art: frames, icons, warning graphics | 9.1 | Decided | In | M2f
HUD-08 | MVP | HUD Screen & Camera | Drone camera: a brief bird's-eye look that never takes away control | 9.2 | Decided | Deferred | CUT | Gated on K6: build it only if hunting the last 1% measures badly
HUD-09 | MVP | HUD Screen & Camera | Colour highlighting on the blocks still standing | 9.2 | Pending | Deferred | CUT | Gated on K6
HUD-10 | Post-launch | HUD Screen & Camera | Figure FIG-13: drone camera highlighting | 付録A | Not drawn | Deferred | -
MAP-01 | MVP | MAP Maps & Intro | Grey-box the ruined seaside city, with the spawn area and deploy point | 10.1 / 12 | Decided | In | B1
MAP-02 | MVP | MAP Maps & Intro | Seaside city kit: buildings, docks, cranes, rubble | 10.1 | Decided | In | M2b
MAP-03 | MVP | MAP Maps & Intro | Dressing passes 1 to 3, and placing the kaiju in the map | 10.1 | Decided | In | B4 / B6 / M2e
MAP-04 | MVP | MAP Maps & Intro | Lighting and skybox | 10.1 | Decided | In | M2e
MAP-05 | MVP | MAP Maps & Intro | Tone: a work site cleaning up after a disaster, never horror | 10.1 | Policy | Gap | - | Gap #14. Nowhere in the plan does this reach the art brief
MAP-06 | Post-launch | MAP Maps & Intro | The ruined city centre as a second map | 10.1 | Decided | Deferred | -
MAP-07 | Post-launch | MAP Maps & Intro | Desert base, snow lab, offshore rig | 10.1 | Decided | Deferred | -
MAP-08 | MVP | MAP Maps & Intro | Opening sequence: the aftermath, the fallen kaiju, the crew arriving, the mission stated | 10.2 | Decided | Deferred | CUT
MAP-09 | MVP | MAP Maps & Intro | A text mission brief in place of the opening movie | 10.2 | Decided | In | B13
MAP-10 | MVP | MAP Maps & Intro | Narrated on the first run, skippable on every run after | 10.2 | Decided | Gap | - | Gap #13. B13 writes the brief but nothing implements the skip
LBY-01 | MVP | LBY Lobby | Deployment gate and kaiju selection | 11.1 | Decided | In | B10
LBY-02 | MVP | LBY Lobby | Difficulty selection, NORMAL only | 11.1 | Decided | In | B10
LBY-03 | MVP | LBY Lobby | The item shop | 11.1 | Decided | In | B11
LBY-04 | MVP | LBY Lobby | Gear and skill upgrades | 11.1 | Decided | In | A14
LBY-05 | MVP | LBY Lobby | Lobby environment, shop stalls and deploy gate models | 11.1 | Decided | In | M2d
LBY-06 | Post-launch | LBY Lobby | The 7-day login bonus | 11.2 | Decided | Deferred | CUT
LBY-07 | Post-launch | LBY Lobby | Daily quests: cut 500 blocks, rescue 2 survivors, drive off 10 larvae, finish a gas event without going down, clear one HARD run | 11.2 | Decided | Deferred | CUT
LBY-08 | Post-launch | LBY Lobby | The kaiju codex | 11.2 | Decided | Deferred | CUT
LBY-09 | Post-launch | LBY Lobby | Records: survivors rescued, enemies killed, blocks cut | 11.2 | Decided | Deferred | CUT
COOP-01 | MVP | COOP Co-op & Networking | Replicate block destruction to four clients: the networking spike | D2 | Decided | In | B7 | The sheet's top risk: nothing in the prototype is multiplayer
COOP-02 | MVP | COOP Co-op & Networking | 1-4 player co-op: shared demolition percentage, player list, join and leave | 3.1 / D2 | Decided | In | B8
COOP-03 | MVP | COOP Co-op & Networking | Handle a player death: rejoining and spectating | 14 N6 | Pending | Gap | O-D | Gap #3. O-D flags it as needed before day 5, but no row builds what happens when one of four players dies
COOP-04 | MVP | COOP Co-op & Networking | Wipe conditions and how the run ends | 14 N6 | Pending | Gap | O-D | Gap #3
COOP-05 | MVP | COOP Co-op & Networking | Measure replication load at four players | — | Verify | In | §9 / Day5
ECO-01 | MVP | ECO Economy & Rewards | Implement in-run income and permanent currency | 14 N10 | Pending | Gap | - | Gap #2. The split is decided in RES-10. B11 and A14 cannot be built until it is clear what they spend
ECO-02 | MVP | ECO Economy & Rewards | Reward tables for clears and for events | 2 / 12 | Pending | Gap | - | Gaps #1 and #2
ECO-03 | MVP | ECO Economy & Rewards | Balance upgrade costs against rewards | 8 / 14 N10 | Pending | Gap | -
ECO-04 | MVP | ECO Economy & Rewards | Shop pricing for the four mask tiers, guns and healing items | 8.2 | Provisional | Gap | -
ART-01 | MVP | ART Art & Level Design | Hazmat suit, laser cutter, gun and gas mask models | 4.1 | Decided | In | M2a
ART-02 | MVP | ART Art & Level Design | Kaiju larva creature and animations | 6.2 | Decided | In | M1c
ART-03 | MVP | ART Art & Level Design | Event-block VFX: organ glow and egg pulse | 5 / 6 | Decided | In | M2c
ART-04 | MVP | ART Art & Level Design | Enforce wholly original designs for kaiju, aliens, UFOs and suits | 付録A ⚠ / 7.1 | Policy | Gap | - | Gap #6. No row covers it, and on the sneakers project 60 copyrighted rigs became a publish blocker
ART-05 | MVP | ART Art & Level Design | Mitigate the difficulty of authoring the octopus, whose tentacles are hard to express in an SDF | 7.1 | Verify | In | §9 | Budgeted at 1.5 days; the fallback is reskinning the existing quadruped body
RES-01 | - | RES Decisions & Validation | N1: settle the target length of one run | 14 N1 | Pending | In | O-C
RES-02 | - | RES Decisions & Validation | N2: settle the acceptable gap between solo and four-player clear times | 14 N2 / 3.2 | Pending | Gap | - | Gap #7. GDD 3.2 calls this out for verification and K2 measures it, but it is not tracked as an open item. It is the only thing that validates D2
RES-03 | - | RES Decisions & Validation | N3: settle block count and kaiju volume | 14 N3 | Pending | In | O-C
RES-04 | - | RES Decisions & Validation | N4: settle the cap on the drone's contribution | 14 N4 | Pending | In | A11
RES-05 | - | RES Decisions & Validation | N5: settle event frequency and the anti-repeat rules | 14 N5 | Pending | In | A12 / A16
RES-06 | - | RES Decisions & Validation | N6: settle death, spectating and wipe conditions | 14 N6 | Pending | In | O-D | An answer is needed before the day 5 co-op work
RES-07 | - | RES Decisions & Validation | N7: settle whether the UFO can be shot down | 14 N7 | Pending | Deferred | O-E | Follows O-B
RES-08 | - | RES Decisions & Validation | N8: settle whether a rescue can fail | 14 N8 | Pending | Deferred | -
RES-09 | - | RES Decisions & Validation | N9: settle reward multipliers by difficulty | 14 N9 | Pending | Deferred | -
RES-10 | - | RES Decisions & Validation | N10: settle how in-run income separates from permanent currency | 14 N10 | Pending | Gap | - | Gap #2. Absent from the open items, yet B11 and A14 on day 6 both depend on it
RES-11 | - | RES Decisions & Validation | Get client sign-off on cutting the UFO event from the MVP | 6.4 / 12 | Pending | In | O-B | GDD ch.12 has it in the MVP. An answer is needed by day 3
RES-12 | - | RES Decisions & Validation | Confirm the dedicated team composition | — | Pending | In | O-A | Closed on 19 September 2026
KPI-01 | MVP | KPI Instrumentation | K1: run completion rate | 15 K1 | Decided | In | A15
KPI-02 | MVP | KPI Instrumentation | K2: clear time, overall and by party size | 15 K2 | Decided | In | A15
KPI-03 | MVP | KPI Instrumentation | K3: ratio of cutting time to event time | 15 K3 | Decided | In | A15 | Core hypothesis
KPI-04 | MVP | KPI Instrumentation | K4: time to return to cutting after an event | 15 K4 | Decided | In | A15 | Core hypothesis: whether the short loop actually closes
KPI-05 | MVP | KPI Instrumentation | K5: drone share of demolition | 15 K5 | Decided | In | A15
KPI-06 | MVP | KPI Instrumentation | K6: time spent hunting the last 1% | 15 K6 | Decided | In | A15 | Decides whether the drone camera is needed at all
KPI-07 | MVP | KPI Instrumentation | K7: damage taken from switching to the wrong tool | 15 K7 | Decided | In | A15
KPI-08 | MVP | KPI Instrumentation | K8: down rate, solo versus co-op | 15 K8 | Decided | In | A15
KPI-09 | MVP | KPI Instrumentation | K9: replay rate on the same kaiju | 15 K9 | Decided | In | A15 | The central hypothesis. EVT-18 means there is no jackpot event, so the reading needs a caveat
KPI-10 | MVP | KPI Instrumentation | The structured event logging pipeline | 15 | Decided | In | A15
KPI-11 | MVP | KPI Instrumentation | Confirm K1 to K9 emit real data from a full run | 15 | Decided | In | B15
REL-01 | MVP | REL Release & QA | Full QA pass: solo and four players, both events, the drone rules, tool separation | — | Decided | In | B12
REL-02 | MVP | REL Release & QA | Verify D7: the drone never destroys an event block | D7 | Decided | In | A18
REL-03 | MVP | REL Release & QA | Verify D9: the cutter does no damage to enemies and the gun does not cut the kaiju | D9 | Decided | In | A18
REL-04 | MVP | REL Release & QA | Balance cutting speed, event frequency and larva strength to a completable run | 14 N1 / N5 | Provisional | In | A16
REL-05 | MVP | REL Release & QA | Bugfix from QA | — | Decided | In | A17
REL-06 | MVP | REL Release & QA | Publish and place settings | — | Decided | In | B14
REL-07 | MVP | REL Release & QA | Definition of done: a 1-4 player run reaches 100% demolition and ends cleanly | — | Decided | In | B12 | Cannot be met without LOOP-03 and LOOP-04
REL-08 | MVP | REL Release & QA | Resolve the 12-hour overload on Dev A on day 4 | — | Pending | Gap | - | From the hour check: A8 3h plus A9 4h plus A10 5h. Dev A has only 6h on day 5, so move A10 or A9. Days 2 and 3 also run to 9h
REL-09 | MVP | REL Release & QA | Resolve the same-day dependency where A7 on day 3 waits on M1c, also on day 3 | — | Pending | Gap | - | From the hour check: A7's 5h cannot start until M1c's 8h lands, which pushes it into day 4
REL-10 | MVP | REL Release & QA | Fix the chapter misattribution in the sheet's section 6 regarding suit recolouring | 11.1 / 11.2 | Decided | Gap | - | Misread: filed under 11.2 retention features, but GDD 11.1 lists it as required at launch
REL-11 | MVP | REL Release & QA | Record the deliberate deviation from HUD 9.1 in dropping the drone camera toggle | 9.1 | Decided | Gap | -

## Spec Gaps (EN)
# | Type | Item | Source | Current state | Impact | All Tasks ID
G01 | Missing | Run end, rewards and the return to the lobby | GDD 2 ⑦⑧ / 12 | A3 stops at counting the percentage. Nothing builds the clear sequence, the result screen, the reward payout or the trip back to the lobby | The tail of the long loop is missing, so the definition of done cannot be met | LOOP-03 / LOOP-04 / ECO-02
G02 | Missing | Currency and reward design | GDD 14 N10 | N10 does not even appear in the open items | B11 and A14 cannot be built until it is clear what they spend, so both day 6 tasks hang | ECO-01 to ECO-04 / RES-10
G03 | Missing | Death, spectating and wipe handling in co-op | GDD 3.1 / 14 N6 | O-D raises the flag, but B8 covers only the shared percentage, the player list and join/leave | Nothing builds what happens when one of four players dies, which day 5 depends on | COOP-03 / COOP-04 / RES-06
G04 | Missing | The visibility loss from the gas itself | GDD 6.1 | A8 ports the existing hazard and A9 does the mask tiers. The sheet's own audit says no tiers or FOV effect | No row builds 6.1's gas filling the screen. M2c is event-block VFX, a different thing | EVT-04
G05 | Missing | The gun line-up and how weapons differ | GDD 8.2 | A6 builds one gun; B11 sells guns, plural | How many guns ship is undefined, and nothing differentiates them by damage, area, rate of fire or knockback | TOOL-07 / TOOL-08
G06 | Missing | The originality check | GDD 付録A ⚠ / 7.1 | No row covers it | It covers kaiju, aliens, UFOs and suits. On the sneakers project 60 copyrighted rigs became a publish blocker | ART-04
G07 | Missing | N2, the acceptable gap between solo and four-player clear times | GDD 3.2 / 14 N2 | Absent from the open items, though K2 measures it | GDD 3.2 calls it out for verification. It is the only thing that validates D2 | RES-02
G08 | Missing | FIG-12, the HUD mock, is undrawn while implementation runs ahead | GDD 付録A / 9.1 | The figure is not drawn | B9 builds the HUD on day 5 and M2f does the UI art on day 6, so the HUD precedes its own mock | HUD-06
G09 | Missing | The drone peeling around a buried event block | GDD 5.3 | A10 stops at never event blocks | Clearing the covering blocks and leaving the core standing is separate adjacency work, and it is the subtle part of D7 | DRN-03
G10 | Missing | Art brief condition 3: volume to bury event blocks in | GDD 7.1 | M1a covers conditions 1 and 2 only | B6 verifies climb routes and interior access, but never the volume | KJU-05
G11 | Missing | Party-size scaling in the event roll | GDD 6.6 | A12 covers anti-repeat and single events at low percentages only | More enemies at four players but never four times the events is missing | EVT-17
G12 | Missing | The drone camera toggle in HUD 9.1 | GDD 9.1 | Omitted from B9's description | Even as a consequence of cutting the camera, it should be recorded as a deviation from 9.1 | HUD-05 / REL-11
G13 | Missing | The narrated first run and the skip after it | GDD 10.2 | B13 writes the text brief only | Nothing implements narrated on the first run and skippable after | MAP-10
G14 | Missing | The tonal direction for the map | GDD 10.1 | It appears nowhere in the plan | A work site cleaning up after a disaster, not horror, never reaches the art brief | MAP-05
M01 | Misread | Suit recolouring filed under the wrong chapter | GDD 11.1 vs 11.2 | The sheet's section 6 defers it as an 11.2 retention feature | It sits in 11.1, required at launch, and 8.2 sells it in the shop. 11.2 holds the login bonus, dailies, codex and records. The fix is one line in B11 | PRG-08 / REL-10
S01 | Schedule | Dev A's daily hours run over eight | — | Day 2 9h, day 3 9h, day 4 12h, and Dev B at 10h on day 5. Dev A totals 67h | Day 4 is A8 3h plus A9 4h plus A10 5h, and it is also the co-op go/no-go day while Dev B runs the 6h B7 spike. Dev A has only 6h on day 5, so A10 or A9 can move | REL-08
S02 | Schedule | A7 depends on M1c on the same day | — | A7, the egg event on day 3 at 5h, depends on M1c, the larva model on day 3 at 8h | A7 cannot start until M1c's 8h lands, which pushes it into day 4 — already a 12-hour day | REL-09
D01 | Design risk | Both MVP events are crises | GDD 6.6 / 6.3 / 15 K9 | Gas and larvae only. Survivors, 6.3, and the UFO, 6.4, are both cut | 6.6 states that positive events must be mixed in so it is not crisis after crisis, and the MVP structurally cannot do that. The central hypothesis is measured by K9, the replay rate, so with no jackpot event at all the measurement reads the crisis-only build rather than the hypothesis. Survivors need no combat, just a thank-you and a walk-off, and their failure condition is still undecided under N8 — so they may well be cheaper than larvae, which cost A7 5h plus M1c 8h plus a chase AI | EVT-18 / EVT-10 / KPI-09

## Work Log
Date | Task ID | Work done | Status | Question / Blocker | Answer | Notes
2026-09-22 | A1 | Created the KAITAI place | Done | Is the folder structure and server-authoritative layout (A1 scope) also in place, or only the place itself? |  | Sheet A1 = place + folder structure + server-authoritative layout
2026-09-22 | M1a / KJU-01 | Added the octopus kaiju model to the place | Done | 1) Is this a mesh blockout only, or already converted to the cube block system (A4)? 2) Does the pose give at least 2 climb routes and a mouth/interior opening (KJU-03, KJU-04)? 3) Is there enough body volume to bury event blocks (KJU-05)? |  | Octopus is the long pole per plan §8
2026-09-22 | A2 |  | Not started | Has KaijuBlockBuilder been ported from the pirate place yet? A3, A4, A5 all depend on it. |  | Day 1 task, blocks the rest of Dev A
2026-09-22 | A1 / B2 | Folder layout: ReplicatedStorage.Config, ReplicatedStorage.Remotes, ServerScriptService.Server, ServerStorage.Assets. Five Config ModuleScripts: RunConfig, KaijuConfig, ToolConfig, EventConfig, DroneConfig. All numbers provisional and commented with GDD refs. Fixed Octopus_Kaiju BlockSize attribute 4 -> 40. | Done | 1) Does the player start with a Lv1 mask, or must every mask be bought? 2) Lobby vs on-site purchases: sheet 3.2 suggests equipment in lobby, upgrades on site. Confirm. 3) Block HP values are invented; is there a v0.3 number for cutter speed or block toughness? |  | Added RunConfig as a 5th module for run-level rules (party size, HP, run length). Sheet named four; split keeps KaijuConfig about the body only.
2026-09-22 | Decision | Skip A2 port and A4 SDF re-authoring. Build demolition directly on the 1,350-block Octopus_Kaiju model. Keep 40-stud blocks for MVP. | Agreed |  | Agreed by Shayan 2026-09-22 | Removes most of the B7 networking spike: anchored Part destruction replicates from the server for free.
2026-09-22 | A3 / LOOP-01 / LOOP-02 | Demolition system. ServerScriptService.Server.Demolition (ModuleScript) is the single entry point: Damage(block, amount, source) with per-block HP from KaijuConfig.BlockHP, Break(), CanDamage(). ReplicatedStorage.RunState folder carries TotalBlocks, RemainingBlocks, DemolitionPercent, State as attributes for the HUD. Cleared event fires at 0 remaining. Per-source contribution tracked for K5. Externally destroyed blocks are still counted so the percent cannot drift. Server.Main bootstraps it. | Done | 1) On clear, what happens next? LOOP-03/04 (result screen, reward payout, lobby return) have no task rows. Currently prints to output only. 2) Should the drone contribution cap (N4) be enforced live (drone pauses when its share exceeds 40%) or only measured? |  | D7 and D9 enforced inside CanDamage so every caller inherits them; A18 verification can target this one function. Tested in run mode: damage/break, gun refused, drone refused on Organ, external destroy counted, full clear reaches 100.00 and fires Cleared.
2026-09-22 | A5 / TOOL-01 | Laser cutter. StarterPack.LaserCutter (Tool: Handle cylinder, Muzzle attachment, ServerBeam, Client LocalScript). Client raycasts camera->mouse against the kaiju only, reports the aimed block over Remotes.CutterAim at 10 Hz, and draws a local beam every frame. ServerScriptService.Server.Cutter validates equip, alive, reach (Range 90 + block half-diagonal) and Demolition.CanDamage, then applies Cutter.DPS x level Mult per Heartbeat. 0.5 s report timeout stops cutting. Server beam shown to others, hidden for the wielder. CutterLevel player attribute drives the multiplier (A14 will set it). | Done | 1) Cutter has no SFX/VFX assets yet (beam is a placeholder texture). Who supplies the cut loop sound and hit sparks: M2c or M1d? 2) Should blocks show damage before breaking (color darkening, cracks)? Not in any task row. 3) Tool lives in StarterPack until B5 inventory takes over. OK? |  | D9 holds by construction: Cutter only ever calls Demolition, never a Humanoid. Tested in play mode: Light block (HP 40) breaks after ~0.4 s of aim; far block rejected with no HP change; wielder ServerBeam forced off, LocalBeam present; damage freezes within 0.5 s after reports stop.

## Build Plan
Dismantle - Build Plan |  | Questions, work done and the build order. Started 2026-09-22. Ask in OPEN QUESTIONS, answer in column H. Log finished work in WORK DONE. Task IDs refer to the tasks / All Tasks tabs.
1. RESEARCH |  | Competitor and community scan, 2026-09-22
ID | Type | Item | Detail | Source / Spec | Owner | Status | Answer / Result | Date
R01 | Reference title | Flatten The Mountain (DomBlox Games, Roblox) | Created 2026-08-18, last updated 2026-09-14. 4.47M visits, 213 playing at time of check, 20 max players per server, 20,348 up / 1,443 down (93%), 18,492 favorites. Genre: Incremental Simulator. | roblox.com/games/78724109436030 ; games.roblox.com API |  | Done |  | 2026-09-22
R02 | Reference loop | Mine blocks -> Cash -> Skill Tree (Player: Damage / Mine Speed; Drones; Turrets) | Early prices: Damage I $1, Drone I $5, Turret I ~$23, so the first purchase lands within seconds of joining. Wiki numbers are dated Sep 1-3 and have already shifted: tuning happens without a public changelog. | flatten-themountain.wiki |  | Done |  | 2026-09-22
R03 | Reference economy | Two currencies: Cash (in-run, skill tree) and Gems (chests + layer completion, spent in the lobby Pickaxe Store) | This is the reference answer to our Gap G02 / N10: in-run cash spent on site, persistent gems spent in the lobby. | flatten-themountain.wiki |  | Done |  | 2026-09-22
R04 | Reference hazard | Eagle event: "EAGLE INCOMING!" alert, red warning path, move out or take damage; intensifies near the summit | One telegraphed hazard is the reference signature moment and its marketing hook. Same shape as our cut UFO laser (6.4 / O-B). | flatten-themountain.wiki |  | Done |  | 2026-09-22
R05 | Reference community tips | Drones before turrets ("laser poverty" if turrets only); workers before cosmetics; terraces not tunnels ("swiss cheese"); public servers split sides via chat | Confirms drone as the first automation buy (matches D6). Cosmetic spending is a known newbie trap, so suit recolor should be cheap and late. | flattenthemountains.wiki/guides/how-to-flatten |  | Done |  | 2026-09-22
R06 | Direct competitor | Kaiju Cleanup (Steam, Mythwright + Brightrock Games, 2026, unreleased, playtest sign-ups open) | Same premise: 1-4 co-op cleanup crews carve kaiju corpses with laser cutters, claw out organs, acidic fluids, radiation, explosive organs, death -> clone respawn, powerwash debris. Meta: upgrade tools, customize base / van / outfit, grow "KaijuCorp", kaiju codex. Tags: Relaxing, Funny, Casual, cartoonish gore. Announced TGS 2025, co-op trailer May 2026. | store.steampowered.com/app/3729700 ; monstervine.com |  | Done |  | 2026-09-22
R07 | Competitor takeaway | Not on Roblox, so no audience clash, but the naming and premise overlap is real | Our differentiator must be the block-incremental loop plus random buried events, not "clean up a kaiju". Feeds ART-04 originality check and the title decision (GDD 9.2). Their relaxing / funny tone matches our v0.2 gas direction and MAP-05. | R06 ; GDD 9.2 ; MAP-05 |  | Done |  | 2026-09-22
R08 | Genre conventions | Roblox simulator retention: first upgrade inside 30 s; rebirth / prestige for long-term; Mining Simulator added 4-member guilds and enchanting; Mine a Mountain rebalanced its mid-game economy | The run-end -> lobby -> persistent upgrade tail (Gap G01) is the retention layer. Ship at least one visible persistent upgrade after run 1. | devforum.roblox.com ; kitsblox.com ; fandom changelogs |  | Done |  | 2026-09-22
R09 | Not found | No public changelog for Flatten The Mountain; no Reddit / DevForum complaint threads indexed | Next: check the DomBlox Discord and in-game update board by hand; watch the wiki price snapshots for tuning direction. | - |  | Done |  | 2026-09-22
R10 | Reference cutting model | Flatten The Mountain digs a large logical block from the inside: discrete hits, hit position picks an internal cell, cells have HP, a hit can take 1-3 cells ("three-voxel break" at Damage I), cavities appear, the block completes when its material is gone | Repo spec Progress/modules "Flatten The Mountain - Digging" sections 9-12, 19-21, 27 (from gameplay video); wiki confirms the three-voxel break. Our cutter instead treats the whole 40-stud block as one HP pool with a continuous laser. Same outcome (block gone, percent up), no cavity feel. Decision needed: Q23. | Progress/modules ; flatten-themountain.wiki |  | Done |  | 2026-09-22
R11 | Reference feedback loop | White outline on the aimed block; +$ shown only on block completion, never per hit; next target re-outlined | Adopted 09-22: LaserCutter client now draws a white Highlight on the aimed block, and damaged blocks fade (Transparency up to 0.5) as a stand-in for cracking. Reward on completion waits on the currency decision (Q04). | Repo spec sections 3, 19-21 |  | Done |  | 2026-09-22
R13 | Cutting polish research (09-22) | No public source-level information on Flatten The Mountain cutting exists: no devlog, Discord notes or DevForum posts by DomBlox; clip titles carry nothing | Best evidence stays the repo video-derived specs: large logical block with internal cells, discrete spatial hits removing 1-3 cells, cavities, +$ on completion, white outline. Community recipes adopted: absolute-base-size punch tween (no drift), debris that falls not flies, pooled and capped shards, all FX client-side. Decisions locked in the Cutting Polish Plan. | Progress/modules ; DevForum squash-stretch thread ; Block Break & Debris plan (09-14) |  | Done |  | 2026-09-22
R14 | Kaiju skin texture research (09-23) | How Roblox block / voxel games texture tens of thousands of Parts: (1) built-in Enum.Material (PBR, tinted by Color, zero assets); (2) MaterialVariant via MaterialService: a custom tileable PBR material (color + normal + roughness + metalness) assigned by name, no extra instances per part, StudsPerTile controls the tile; (3) Texture / Decal instances: 6 per Part, so 43k parts would mean about 260k instances, rejected by every performance thread; (4) SurfaceAppearance: MeshParts with UVs only, not applicable to Parts; (5) Studio Texture Generator (AI): MeshParts only. | Recommendation: Phase 1 now, no upload: map each BlockMaterial to a built-in material + colour (Skin Cobblestone for scale plates, Flesh Mud, Sucker Pebble, Ridge Slate, Eye Glass, Light and Event Neon so they glow) and keep the per-block tint. Phase 2 when art is ready: 3 to 4 uploaded MaterialVariants (1024x1024 tileable, colour + normal + roughness, low contrast so Color tints them) assigned by name; StudsPerTile 2.667 makes one tile per chunk and a 3x3 grid per block, which also solves the voxel look. Known caveat: variants tile from the face centre, fine for our uniform 8 and 2.67 stud parts. Creator Store PBR material packs are a no-artist route for Phase 2. | devforum: Materials v Custom Textures (503161), MaterialVariant performance (2590033), tiling origin (2203997) ; create.roblox.com/docs/parts/materials ; docs/art/modeling/surface-appearance |  | Done |  | 2026-09-22
R15 | Reference skill tree (Drones.txt, 09-23) | Transcription of Flatten The Mountain's on-site upgrade tree. Player: Damage I-XVI (voxels per swing: III $20 4>5, V $100 6>7, XVI $34,800), Mine Speed I-VI (swings/s: II $60 4>5, IV $1,000 6>7, V $5,000), Mine Distance I-II (I $150 = 18 studs), Auto Mine $800 (hold to mine, player still aims). Drone: count I-VII, Damage I-IV, Rate I-IV, Speed I-V (III $1,940 14.4>19.2 studs/s, IV 19.2>24). Turret: count I-V ($1,035 at V), Damage I-V (voxels per tick, II-IV $20/$60/$120 for 2>5), Rate I-IV (III $60 = 4 ticks/s), Orbit Speed I-VI ($10-$80, 16>50 deg/s), Aim I-III (II $500 20 deg, III $10,350 30 deg), Pierce I-II ($5,000 20% hit-behind, II $13,900). Only nodes the transcriber stood on carry numbers. | Damage is voxels per swing (our cells per hit already match the model; their Lv1 is 3-4 voxels of a block, ours 9 of 27). Rate is its own axis (4-7 swings/s; our HitInterval is fixed). Range is short (18 studs vs our 90, Q24). Auto Mine is paid there and free here (our laser is hold-to-cut). Prices run $10 to $35k, so $1 per block on a 35k-block kaiju buys about one late node (Q04 / Q26 are one problem). Turret axes Aim and Pierce have no equivalent in our plans. | Drones.txt (repo root) |  | Done |  | 2026-09-22
R16 | Design drawing (Understanding through drawing.pdf, 09-23) | Three hand-drawn pages by Shayan. Page 1: HUD with a top percent bar, kaiju silhouette, four slots (fourth crossed out), "view" and "upgrade" buttons on the right; slots Gas Mask, Gun ("X block"), Laser Cutter ("for both"). Page 2: event block drawn as a grid with a hatched inner cell, "different colour"; outcomes 1 Gas (green block, arrow to the mask), 2 Egg (larva), Survivor (stick figure + coin), Health (cross), UFO (saucer beaming a figure onto a red block). Page 3: Drone and Player both cut blocks, drone "cannot break event block"; Gun axes "damage, rate, area of fire". | Confirms D7 and D9 as built and the event-inside-a-block model. New: the cutter must damage enemies too (built, W34); three event outcomes we do not have (Survivor with cash, Health pickup, UFO, Q28); gun gets an area-of-fire axis (Q29); the shop lives on the HUD on site (part of Q03); event type telegraphed by colour (green gas, red UFO). | Understanding through drawing.pdf (repo root) |  | Done |  | 2026-09-22
R12 | Reference upgrade axes | Player: Damage, Mine Speed, Mine Distance (18 studs at tier I), Auto Mine (~$200). Drones I-IV: Damage, Rate, Speed, Range. Turrets I-III: Damage, Rate, Orbit Speed. Opening: Damage I ($1) -> Drone I ($5) -> Mine Speed -> Turret I (~$23) -> Mine Distance -> Auto Mine | Maps to ours: Damage = Cutter.DPS, Mine Speed = LevelMult, Mine Distance = Cutter.Range (ours is 90 because a 40-stud block needs it; theirs is 18 and forces proximity). Auto Mine is a cheap, popular node worth a slot on our cutting axis (PRG-01). | flatten-themountain.wiki/skill-tree |  | Done |  | 2026-09-22
2. OPEN QUESTIONS |  | Ask here. Answer in column H, set Status to Answered, add the date.
ID | Type | Item | Detail | Source / Spec | Owner | Status | Answer / Result | Date
Q01 | Question | Octopus model state | Is Octopus_Kaiju a mesh blockout or already the 1,350-block cube model? Does the pose give 2 climb routes, a mouth opening, and enough volume to bury event blocks (KJU-03 / 04 / 05)? | Work Log 09-22 ; Gap G10 | Modeller 1 / Shayan | Answered | Answered 09-22 from kaiju.rbxl: already the cube model, 1,350 anchored 40-stud Parts, tagged BlockMaterial (Skin 582, Flesh 566, Light 100, Sucker 68, Ridge 30, Eye 4) and Region (Mantle 996 + Arm01-08). Bury volume OK: 566 Flesh blocks are fully enclosed. Mouth / interior opening: NONE (0 cavities). Climb routes: NONE, see Q19. | 2026-09-22
Q02 | Question | Starting mask | Does the player spawn with a Lv1 mask, or must every mask be bought? Decides how the first gas event on run 1 feels. | Work Log ; TOOL-03 / 04 | Design | Answered | Answered 09-22 by Shayan: every player spawns with a Lv1 GasMask (ToolConfig.Mask.StartingLevel). Built as W18. | 2026-09-22
Q03 | Question | Purchase location | Equipment in the lobby, upgrades on site (Supplementary Notes 3.2)? The reference does the skill tree on site with Cash and pickaxes in the lobby with Gems. Confirm the split. | Supp. Notes 3.2 ; R03 | Design | Open |  | 2026-09-22
Q04 | Question | Currency model | One currency or two? If two: in-run Cash for cutter / drone levels, a persistent currency for the shop. B11 and A14 (Day 6) cannot start without this. | Gap G02 / N10 ; R03 | Design / Client | Open |  | 2026-09-22
Q05 | Question | Block HP and cutter speed | Block HP values in KaijuConfig are invented. Does v0.3 give cutter DPS or block toughness numbers? | Work Log ; SET-04 | Design | Open |  | 2026-09-22
Q06 | Question | Run end | On 100% clear: result screen? reward payout? automatic return to the lobby? Today it only prints to output. No task row exists (LOOP-03 / 04). | Gap G01 | Design / Client | Open |  | 2026-09-22
Q07 | Question | Drone cap | Enforce N4 live (drone pauses when its share passes 40%) or only measure it through K5? | Work Log ; DRN-05 | Design | Answered | Provisional 09-22: enforced live AND measured. DroneConfig.EnforceShareCap = true pauses the drone over 40% share (also satisfies DRN-06: a drone alone can never clear a run). Flip the flag to measure-only. Confirm or change. | 2026-09-22
Q08 | Question | Cutter FX owner | Who supplies the cut loop SFX and hit sparks: M2c or M1d? Should blocks show damage (darkening, cracks) before breaking? | Work Log | Art lead | Open |  | 2026-09-22
Q09 | Question | Death handling | When one of four dies: spectate, respawn, or downed + revive? Is a full wipe a run failure? Kaiju Cleanup uses clone respawn. Needed before B8 on Day 5. | Gap G03 / N6 ; R06 | Design / Client | Open |  | 2026-09-22
Q10 | Question | UFO cut sign-off | Client sign-off to cut the UFO laser from MVP (O-B), due Day 3. Note: the reference eagle shows a telegraphed hazard is cheap and memorable. Keep it parked or reconsider? | O-B ; R04 | Client | Open |  | 2026-09-22
Q11 | Question | Only-crisis events | Gas and larva are both crises (6.6 says mix in positive events). Add survivors (no combat) or a chest-like positive egg outcome instead of, or before, the larva? | Gap D01 ; EVT-18 | Design / Client | Open |  | 2026-09-22
Q12 | Question | v0.3 spec missing | The task list is built on "Core Loop & Base Specification v0.3" (2026-09-19). It is not in the repo. Add the PDF to gdd/. | plan tab section 1 | Shayan | Open |  | 2026-09-22
Q13 | Question | Turret plans | Progress/modules holds Turret System and Upgrade ladder plans (Sep 16). D6 drops turrets. Shelve as post-MVP? | D6 ; repo | Shayan | Open |  | 2026-09-22
Q14 | Question | Server model | 4-player private party, or public server up to 20 like the reference? Changes B7 / B8 and lobby matchmaking. | D2 ; R01 | Design / Client | Open |  | 2026-09-22
Q15 | Question | Title overlap | Kaiju Cleanup (Steam 2026) uses almost the same premise. Any concern for the title and store naming? | R06 / R07 ; GDD 9.2 | Client | Open |  | 2026-09-22
Q16 | Question | Run length | 15 min provisional (O-C). Confirm so N3 block count can be fixed. | O-C / N1 | Design | Open |  | 2026-09-22
Q17 | Question | Solo vs 4-player gap | Acceptable clear-time gap between solo and 4 players (N2)? It is the only thing that validates D2. | Gap G07 | Design | Open |  | 2026-09-22
Q18 | Question | Tool placement | LaserCutter lives in StarterPack until B5 inventory lands. OK? | Work Log | Dev B | Open |  | 2026-09-22
Q19 | Question | Climb routes at 40-stud blocks | Default jump (JumpPower 50) clears about 7 studs. Every block is 40 studs, arms are 1-2 layers (40-80 studs), mantle is 7 layers (280 studs). A player cannot get onto the kaiju at all, and cannot climb back up once a layer is cut. Options: (a) climbable TrussPart scaffolds auto-placed on cut faces, fits the work-site tone and is cheap; (b) shrink blocks to 20 studs, about 10,800 parts; (c) treat the kaiju as carve-from-ground only with a ranged cutter, upper layers stay out of reach. Recommend (a) for MVP. | KJU-03 ; kaiju.rbxl check | Design / Shayan | Answered | Answered 09-22 by Shayan: scaffolds. Built as W11. | 2026-09-22
Q20 | Question | Mouth or interior opening | The model has no cavity or opening (KJU-04). Add a mouth pocket in the mantle, or drop KJU-04 for MVP and rely on cutting to expose the interior? | KJU-04 ; kaiju.rbxl check | Design / Modeller 1 | Open |  | 2026-09-22
Q21 | Question | Where is the Day 1 code? | kaiju.rbxl (Downloads, unpublished, placeId 0) has ServerScriptService, ReplicatedStorage and StarterPack empty. The Work Log rows for A1 / B2 / A3 / A5 (Configs, Demolition, LaserCutter) are not in this file, and Kaiju.BlockSize is still 4 not 40. Another file, or unsaved? If none, rebuild here first. | Work Log 09-22 ; kaiju.rbxl check | Shayan | Answered | Answered 09-22 by Shayan: fresh project, nothing elsewhere. Rebuilt A1 / B2 / A3 / A5 in kaiju.rbxl (W01, W04, W05). | 2026-09-22
Q22 | Question | Event blocks not designated | All 1,350 blocks are Demolishable with no Organ / Egg material. Which Flesh blocks become gas organs and eggs, and how many for a 15-min run? Needed before A7 / A8. | EVT-01 ; kaiju.rbxl check | Design | Answered | Provisional 09-22: EventConfig.Seed retags 35 Flesh blocks as "Event" at run start, random each run; the outcome (Gas or Egg) is rolled when the block breaks (W20, EVT-02). Count still needs the N5 frequency decision. | 2026-09-22
Q27 | Question | Kaiju skin: built-in materials now, uploaded variants later? | Approve Phase 1 (built-in materials per BlockMaterial, one config table, applied by the generator and on crack; no upload, reversible in one line) and Phase 2 (artist or Creator Store PBR tiles as MaterialVariants, StudsPerTile 2.667)? Also: should Light and Event blocks glow (Neon)? | R14 | Shayan / Art lead | Answered | Answered 09-23 by Shayan: Phase 1 yes, built (W30). Phase 2 (uploaded MaterialVariants) waits for art; Neon glow on Light and Event blocks adopted. | 2026-09-22
Q28 | Question | Event outcomes from the drawing: Survivor, Health, UFO | The drawing lists five outcomes for an event block: Gas and Egg (built), Survivor (stick figure + coin: rescue pays cash), Health (cross pickup), UFO (saucer beams a figure onto a red block). Build Survivor and Health as the positive outcomes Q11 asked for? UFO contradicts the pending O-B cut (Q10): in or out? Should the block colour telegraph the type before it breaks (green gas, red UFO), or only the hatched inner cell? | R16 ; Q10 ; Q11 ; W20 | Shayan / Client | Open |  | 2026-09-22
Q29 | Question | Upgrade axes for MVP (reference tree + drawing) | The reference sells Damage, Mine Speed (rate), Mine Distance and Auto Mine for the player, count / Damage / Rate / Speed for drones, and six turret axes. The drawing gives the gun damage, rate and area of fire. Our cutter has a damage axis only (LevelMult, CellsPerHitByLevel). Which axes go into the Upgrade System Plan for MVP: cutter rate (HitInterval per level), cutter range (18 studs there vs 90 here, Q24), gun area of fire, drone speed? Auto Mine stays free? | R15 ; R16 ; Q24 ; Upgrade System Plan | Shayan / Client | Open |  | 2026-09-22
Q30 | Question | Economy scale: cash per block vs node prices | Reference node prices run $10 (Orbit Speed I) to $34,800 (Damage XVI). Our provisional Cash is $1 per completed block, and the kaiju has 35,134 blocks, so a full clear buys one late node. Either cash per block scales with material / depth, prices are an order of magnitude lower, or cash is paid per chunk. Decide together with Q04 (currency) and Q26 (balance). | R15 ; Q04 ; Q26 ; RunConfig.CashPerBlock | Shayan / Client | Open |  | 2026-09-22
Q31 | Question | Cutter vs larva damage split | The cutter now damages larvae (W34) at ToolConfig.Cutter.EnemyDPS = 40, below the gun's 50 DPS, so the gun stays the anti-larva tool but a cornered player is not helpless. Approve 40, or make the cutter clearly weaker (20) or equal? Telemetry's LarvaWithoutGun metric still counts damage taken while not holding the gun; rename or keep? | W34 ; R16 ; ToolConfig.Cutter | Shayan | Open |  | 2026-09-22
Q26 | Question | Balance for the large kaiju | 35,134 blocks is 27x the material of the 1,350-block body. Balance now reads 238.6 min of pure solo cutting against a 9.8 min budget (24x over). Per-hit feel is unchanged, so this is a design call, not a knob: (a) raise the run target for a big kaiju, (b) give the cutter area damage that grows with level (hits remove several blocks), (c) make automation (drones, later turrets) carry the bulk as the GDD intends, (d) 4-player sizing. Likely a mix of b and c. Until decided the run is not completable in 15 min. | W29 ; Balance line ; N1 / N4 | Shayan / Client | Open |  | 2026-09-22
Q24 | Question | Ranges after the 8-stud rescale | The kaiju is now 280 x 56 x 264 studs with 8-stud blocks (was 1400 x 280 x 1320 with 40-stud blocks). Ranges were tuned for the big one: cutter Range 90 reaches a third of the body, drone SearchRadius 120 half of it, gas Radius 60 covers 7 blocks, egg AggroRange 250 the whole site. Keep the small kaiju and shrink the ranges (suggest cutter 30, drone search 40 / range 20, gas radius 16, aggro 80), or is the model going to be scaled back up? | W28 ; ToolConfig / DroneConfig / EventConfig | Shayan | Open |  | 2026-09-22
Q25 | Question | Scaffolds still needed? | An 8-stud block is barely above the 7.2-stud jump, and 2.67-stud chunk terraces are walkable once a face opens. The scaffold truss (now 8 studs tall) may be redundant. Keep, or drop and let terraces do the climbing? | Q19 ; W11 ; W28 | Shayan | Open |  | 2026-09-22
Q23 | Question | Whole-block HP or internal cells? | The reference digs cavities inside a large block (R10). Ours removes a whole 40-stud block after one HP pool drains. Keep whole-block for MVP and test the feel (GDD 9.3 item 1), or split each block into internal cells now? Splitting touches Demolition, scaffolds, event exposure and part count. Recommend: keep whole-block for the 8-day MVP, revisit after K3 / K4 measurements. | R10 ; Coverage Matrix open item B | Design / Shayan | Answered | Answered 09-22 by Shayan: polish the cutting now. Internal cells adopted (2x2x2, configurable) with discrete hits; see W25 and the Cutting Polish Plan. | 2026-09-22
3. WORK DONE |  | One row per finished item. Detail says what exists and how it was tested.
ID | Type | Item | Detail | Source / Spec | Owner | Status | Answer / Result | Date
W01 | A1 / B2 | Place, folders, Config modules | ReplicatedStorage.Config / Remotes, ServerScriptService.Server, ServerStorage.Assets. Five Config ModuleScripts: RunConfig, KaijuConfig, ToolConfig, EventConfig, DroneConfig, all provisional with GDD refs. | SET-01 / SET-03 | Dev A | Done | Rebuilt in kaiju.rbxl 09-22 (fresh project, Q21 closed). ReplicatedStorage.Config / Remotes / RunState, ServerScriptService.Server, ServerStorage.Assets (Creatures / Props / VFX). | 2026-09-22
W02 | M1a / KJU-01 | Octopus kaiju model in the place | BlockSize attribute fixed 4 -> 40. | KJU-01 | Modeller 1 | Done | Verified in kaiju.rbxl: Workspace.Kaiju, 1,350 Parts. BlockSize attribute fixed to 40. | 2026-09-22
W03 | Decision | Skip A2 port and A4 SDF re-author | Build demolition directly on the 1,350-block Octopus_Kaiju with 40-stud blocks. Anchored Part destruction replicates from the server for free, which removes most of the B7 spike. | plan tab section 9 | Shayan | Agreed | Reconfirmed: kaiju.rbxl is the 1,350-block cube model | 2026-09-22
W04 | A3 / LOOP-01 / 02 | Demolition module | Server.Demolition: Damage / Break / CanDamage. RunState attributes for the HUD. Cleared fires at 0 remaining. D7 and D9 enforced in CanDamage so every caller inherits them. Per-source share tracked for K5. Tested: full clear reaches 100.00. | LOOP-01 / 02 ; D7 / D9 | Dev A | Done | Rebuilt in kaiju.rbxl 09-22. Run-mode test passed: gun refused (D9), drone refused on Organ (D7), partial damage writes HP attribute, external Destroy still counted, full clear reaches 100.00 and fires Cleared. | 2026-09-22
W05 | A5 / TOOL-01 | Laser cutter | StarterPack.LaserCutter: client aim at 10 Hz, server validates equip / alive / reach / CanDamage, DPS x level multiplier, 0.5 s timeout. Tested in play mode. | TOOL-01 ; D9 | Dev A | Done | Rebuilt in kaiju.rbxl 09-22. Play-mode test passed: far block rejected, near Light block breaks in about 0.4 s, beam on while cutting, damage freezes after the 0.5 s timeout. Cut = hold mouse while aiming. | 2026-09-22
W06 | Research | Competitor and community scan | Rows R01-R09 above. | - | Claude / Shayan | Done |  | 2026-09-22
W07 | Sheet | Build Plan tab created | Questions Q01-Q18 raised, plan P00-P12 laid out. | - | Claude / Shayan | Done |  | 2026-09-22
W08 | Check | In-engine audit of kaiju.rbxl | Counted blocks, materials, regions, layers, enclosed volume, cavities, climb reach, and script containers. Results in Q01, Q19-Q22. | P02 / KJU-03-05 | Claude | Done |  | 2026-09-22
W09 | Setup | Workspace.TestArea | Folders Rigs / Models / Showcase for rigs, models and showcasing. Workspace.Kaiju stays at the top level because it is the live run target. | A1 | Claude | Done |  | 2026-09-22
W10 | Note | Place file not yet saved or published | kaiju.rbxl lives in Downloads with placeId 0. Save it into the repo or publish before Day 2 so the work is not lost. | A1 | Shayan | Open |  | 2026-09-22
W11 | Q19 / KJU-03 | Scaffold system | Server.Scaffold: every broken block leaves a 2x40x2 climbable TrussPart flush against a still-standing neighbour (Workspace.Scaffolds). Cleared run removes them. Demolition gained BlockBroken event and BlockAt(pos). | Q19 ; KJU-03 | Claude | Done | Play-mode test: truss 2x40x2 placed 21 studs from the neighbour centre, logged. Decision by Shayan: scaffolds over smaller blocks. | 2026-09-22
W12 | A6 / TOOL-02 | Gun | StarterPack.Gun (primitive handle, model to come) + Server.Gun. D8 unlimited ammo. D9 by construction: module never requires Demolition, only calls Humanoid:TakeDamage on models tagged Enemy. Server checks equip, alive, fire rate, range, and hit-point spoofing. Logs every shot. | TOOL-02 ; D8 / D9 | Claude | Done | Play-mode test with a runtime-only dummy enemy: 2 instant shots count as 1 (fire rate), kaiju block shot has no effect, spoofed far hit rejected, 6 paced shots kill a 50 HP enemy. | 2026-09-22
W14 | B5 / TOOL-05 / 06 | Inventory | StarterPlayerScripts.Inventory: keys 1-4 map to ToolConfig.Slots {LaserCutter, Gun, GasMask, empty}. One press equips (EquipTool swaps the held tool), pressing the held slot unequips, slot 4 logs reserved. Default 10-slot hotbar disabled. Plain 4-box bar until M2f. | TOOL-05 / 06 ; D5 | Claude | Done | Play-mode test: bar shows 1 LaserCutter / 2 Gun / 3 GasMask (not owned) / 4 (empty); key 2 equips Gun, key 2 again unequips, key 4 logs. Key 1 cannot be simulated by the test harness (Roblox core binding), same code path. | 2026-09-22
W15 | A7 / EVT-01 / 06 / 07 | Egg event with cube larva | Server.EventBlocks seeds Egg / Organ into Flesh at run start (placeholder colours). Server.Egg listens to Demolition.BlockBroken: an Egg spawns a 4-stud red cube Larva (Humanoid, tagged Enemy, server-owned) that pathfinds to the nearest player and bites within 6 studs every 1 s. Corpse removed 2 s after death. Swap the cube for M1c's rig in spawnLarva. | EVT-01 / 06 / 07 | Claude | Done | Play-mode test: 20 eggs + 15 organs seeded, D7 holds on a seeded organ, broken egg hatched 1 larva, larva reached the player and bit (100 -> 90), killed larva removed. Gun already kills Enemy-tagged models (W12). | 2026-09-22
W16 | Cutter parity (R11) | Aim outline + damage fade | LaserCutter client draws a white Highlight on the aimed block while held (reference-style target outline). Demolition.Damage raises block Transparency toward 0.5 as HP drops (placeholder cracking). | R11 ; Q08 | Claude | Done | Play-mode test: egg block at 30/60 HP read Transparency 0.25. | 2026-09-22
W17 | A8 / EVT-03 / 05 | Gas event | Server.Gas: breaking an Organ block bursts a translucent green sphere (placeholder for M2c) of EventConfig.Gas.Radius for Duration seconds in Workspace.Hazards. Players inside lose DPS unless holding the GasMask. Sets player attribute InGas for the overlay and K-metrics. One tick loop for all clouds. Logs burst, breathing, enter / leave, dissipate. | EVT-03 / 05 | Claude | Done | Play-mode test: organ break spawned a 120-stud cloud; unmasked 1.6 s cost 8.8 HP (5 DPS); masked in a fresh cloud held HP for 2.5 s; mask off resumed damage; cloud expired on time. | 2026-09-22
W18 | A9 / TOOL-03 / 04 + EVT-04 | Gas mask + gas overlay | StarterPack.GasMask (primitive handle) in slot 3, everyone starts Lv1 (Q02). Server.Mask owns player attribute MaskLevel. Tool client narrows camera FOV per tier (40 / 52 / 62 / 70) while held. StarterPlayerScripts.GasOverlay tints the screen green when InGas: heavy without the mask, light with it. Mask is a held tool, so wearing it means not cutting or shooting (D5, K7). | TOOL-03 / 04 ; EVT-04 ; Gap G04 | Claude | Done | Play-mode test: MaskLevel 1 on join, FOV 40 when worn and 70 when put away, overlay 0.35 unmasked in gas, 0.80 masked, 1.0 outside gas. | 2026-09-22
W19 | A10 / DRN-01..06 | Support drone | Server.Drone: one cube drone per player (DroneLevel attribute, Lv1 at start) hovers by its owner, picks the nearest ordinary block within SearchRadius of the owner and Range of itself, and cuts it through Demolition as source "Drone", so D7 is inherited from CanDamage. Peels ordinary blocks around buried eggs / organs and leaves the event block for the player (DRN-03 / 04). N4 share cap: pauses while Drone / (Drone + Player) broken blocks exceeds MaxShare 0.4, logs pause / resume. Beam to target. Swap the cube body in spawnDrone when the model lands. | DRN-01..06 ; D6 / D7 ; N4 | Claude | Done | Play-mode test: drone deployed on join, took the nearest Light block, paused at 100% share after its first break, resumed once the player had broken 2 (share 33%), dropped a block the moment it was retagged Organ and left it standing, retargeted with beam on when the owner moved next to the kaiju. | 2026-09-22
W20 | A12 / EVT-02 / 15 / 16 / 17 | Event roll policy | Seeding now tags 35 Flesh blocks as a single "Event" material (purple placeholder). Server.EventRoll decides the outcome when one breaks (EVT-02): weighted pick between Gas and Egg, no immediate repeat (EVT-15), below 30% demolition a new event is suppressed while one is active (EVT-16), larvae per egg scale 1 / 1 / 2 / 2 by party size while event count does not (EVT-17). Egg and Gas subscribe to EventRoll.Triggered; hand-placed Egg / Organ blocks still fire directly. RunState carries LastEvent and EventCount. | EVT-02 / 15 / 16 / 17 ; 6.6 | Claude | Done | Play-mode test: 35 Event blocks seeded; first break rolled Egg; second break suppressed with 1 active at 0.2%; after clearing actives the third rolled Gas (no repeat); party of 1 gave 1 larva. All logged with [Roll]. | 2026-09-22
W21 | B9 / HUD-01..04 | HUD | StarterPlayerScripts.HUD: top shared demolition % with bar and blocks left; bottom-left HP text and colour-shifting bar; left edge GAS warning with PUT ON MASK / masked hint; right edge LARVA count; centre banner for KAIJU DISMANTLED / RUN FAILED and a 3 s EVENT flash. Default Roblox health bar disabled. Counts clouds and living larvae from the replicated folders, no extra remotes. Plain text until M2f HUD art. | HUD-01..04 ; Gap G08 | Claude | Done | Play-mode test: percent text and fill track RunState; HP text tracks the Humanoid; GAS x1 / PUT ON MASK unmasked and GAS x1 / masked with the mask; LARVA x1; EVENT: GAS flash text set. HUD-05 drone camera toggle deliberately absent (REL-11). | 2026-09-22
W22 | A15 / KPI-01..11 | Telemetry | Server.Telemetry emits structured "[KPI] <name> <json>" lines: RunStart, PlayerJoined (K9 offline), Event, EventPhaseStart / End, ReturnToCutting (K4), Last1PercentStart (K6), Down (K8), RunEnd with seconds + party (K1 / K2), cuttingSeconds vs eventSeconds (K3), contribution (K5), last1PercentSeconds (K6), wrongToolDamage split GasUnmasked / LarvaWithoutGun (K7), downs (K8). Hooks existing signals only; Cutter publishes a Cutting attribute. Swap Emit for AnalyticsService / HTTP later. | KPI-01..11 ; ch.15 | Claude | Done | Play-mode test: RunStart at t=0; 0.5 s of cutting counted (block broke at 0.53 s, correct); 1.6 s unmasked in gas counted 10 HP as GasUnmasked and 1.5 s of eventSeconds; EventPhaseEnd then a ReturnToCutting sample of 13.8 s; death emitted Down and RunEnd with state Failed. | 2026-09-22
W23 | A16 / REL-04 | Balance pass + guard | Cutter.DPS 100 -> 150, EventCount 35 -> 24, larva unchanged. Server.Balance prints at run start: total block HP, solo throughput, pure-cutting minutes vs a 15 min SOLO target with 35% overhead reserved, and event spacing. Warns when pure cutting exceeds the budget or is under half of it. | REL-04 ; N1 / N5 | Claude | Done | Run start line: 1350 blocks, 94,280 HP, 170 DPS solo -> 9.2 min pure cutting against a 9.8 min budget; one buried event every 56 blocks, about every 23 s of cutting. Needs a real solo playthrough to confirm (K1 / K2). | 2026-09-22
W24 | B13 / MAP-09 / MAP-10 | Text mission brief + first-run skip | ReplicatedStorage.Config.BriefConfig holds the title and five lines (aftermath, crew, tools, drone and scaffolds, 100% clears) so design can edit text without code. Server.Brief keeps a per-player briefed count (DataStore "DismantleProfile" behind pcall, in-memory fallback with one warning while the place is unpublished) as player attribute BriefRuns, and offers Replay(). StarterPlayerScripts.MissionBrief narrates line by line over a dim, hides HUD and inventory while up, closes itself after the last line; from the second run on, SPACE (bound through ContextActionService at high priority, since jump swallows Space in InputBegan) or clicking the hint skips. | MAP-09 / 10 ; Gap G13 ; 10.2 | Claude | Done | Play-mode test: first run narrated 5 lines with no skip and closed itself, server counted 1; replay as a returning player showed SPACE to skip, HUD and inventory hidden, Space skipped at 12 s, server counted 2 (skipped). Persistence across sessions needs the place published with API access (W10). | 2026-09-22
W25 | Cutting Polish (plan + build) | Cells + hit feel | Plan: Progress/modules "Dismantle - Cutting Polish Plan (Cells + Hit Feel).md". Build: a block splits into 2x2x2 cells on first hit, hits are discrete (0.15 s) and land on the cells nearest the hit point, cells per hit 1 / 2 / 3 by cutter level, cell HP = block HP / 8, percent moves per cell, outline on the logical block, drone hits discretely from its own side. Client BlockFX: pop in / pop out / settle on the hit cell from an absolute base size, dust puff, 2 pooled falling shards per broken cell (cap 60, CanQuery off), bigger dust on completion. Sources mirrored under src/. | Cutting Polish Plan ; R10-R12 ; Q23 | Claude | Done | All 8 acceptance tests passed 09-23: corner hit split a block into 8 cells and hit the nearest one (15.6 studs), parent invisible / non-queryable; Skin cell died on the 2nd 5-damage hit and percent moved 0.0093; gun refused on a cell (D9), drone refused on an Event cell (D7), drone cut from its own side; block completed after its last cell with one BlockBroken, scaffold +1; full clear reached 100.00 and fired Cleared; client saw 3 discrete hits, sibling cells popped to 0.90 and overshot to 1.06 then settled with 0.0000 drift, 2 shards per cell pooled with CanQuery off. Two fixes on the way: pop moved from the dying cell to the block's surviving cells (Block Break plan decision E), and Demolition now passes the block explicitly because deferred BindableEvent handlers see the cell already destroyed. EventRoll ignores hits after Cleared / Failed for the same reason. | 2026-09-23
W27 | Tooling | One-call restore from the src mirror | src/serve.js (node, no packages) serves the mirror on 127.0.0.1:8123 with a manifest mapping files to DataModel paths. src/Restore.luau (or the MCP equivalent) fetches every source through HttpService in plugin context, which needs no HttpEnabled setting, the same mechanism Rojo uses. src/Setup.luau recreates every non-script Instance. Full restore of 32 scripts took one call on 09-23. | W26 | Claude | Done | Used for real on 09-23 morning when kaiju.rbxl came back a second time at the post-drone snapshot. Run: node src/serve.js, then Setup + Restore in the command bar, then SAVE. | 2026-09-23
W26 | Incident | Place reverted to an older snapshot | On 09-22 evening the edit DataModel of kaiju.rbxl was found at the post-drone snapshot: EventRoll, HUD, Telemetry, Balance, Brief, the Egg / Gas roll hooks and config edits were gone. Cause: unsaved place reopened (a second place, Vermilion Mask, was open at the time). Everything was re-sent from the conversation and then mirrored into the repo under src/ with a Setup.luau, so a future revert is a re-send. | W10 | Claude / Shayan | Done | Reverted AGAIN by 09-23 morning: the late-09-22 restore was never saved. Restored from src in one call (W27) and verified: server prints [Balance], [KPI] RunStart, [Brief]. The file on disk is still the post-drone snapshot until Shayan saves. SAVE NOW. | 2026-09-23
W28 | Voxel Kaiju (plan + build) | Blocks of 3x3x3 chunks | Plan: Progress/modules "Dismantle - Voxel Kaiju Plan (Blocks of 3x3x3 Chunks).md". Workspace.Kaiju is now a Model of 1,350 Block Models (attributes BlockMaterial, Region, BlockId, GX/GY/GZ, Color, pivot at centre); each block is 27 chunks; only exposed chunks exist as Parts (11,226 at start), hidden ones are revealed as neighbours go, across blocks. Deterministic per-chunk tint gives the voxel look. Demolition v3: occupancy grid, carry-over damage (DPS exact, chunks per hit follow toughness), reveal, percent per chunk. Cutter and drone beams ride an anchor so they survive the chunk dying. Old model kept in ServerStorage.Assets.Kaiju_Blocks_v1. Generator + all sources mirrored in src/. | Voxel Kaiju Plan ; W25 | Claude | Done | Source model had changed to 8-stud blocks (280 x 56 x 264 studs) between the morning test and this build; the generator now reads the block size from the parts (chunk 2.67 studs). Tests 09-23: 5 dmg at a corner removed exactly the nearest chunk and dented the next; a full Lv1 hit removed 8 Skin chunks; block completed after 3 more hits with one BlockBroken and an 8-stud truss; neighbours grew new faces; D9 on a chunk and D7 on an Event block hold; full clear of 1,348 blocks in 1.6 s reached 100.00 with zero chunk Parts left; client saw 4 hits, Model arg on all, chunks popped -0.267 and settled with 0 drift, shards capped. SpawnLocation moved to 30 studs in front of the body (was 430 studs away). | 2026-09-23
W29 | Large Voxel Kaiju | 35,134 blocks, two-level rendering | Shayan: "make the kaiju large, do not scale it". The 1,350-block 8-stud octopus was resampled at 3x resolution as a density field (trilinear, threshold 0.5, so the silhouette rounds off): 35,134 blocks of 8 studs, body 840 x 168 x 792, 21 layers, generated in 1.9 s. Rendering is two-level like the reference: intact exposed block = one voxel Part in Workspace.Kaiju (8,258 at start); intact hidden block = Part parked in ServerStorage.KaijuHidden, never replicated (26,876); a block cracks into a Model of exposed 3x3x3 chunk Parts on its first hit. Removing chunks reveals hidden chunks and un-parks hidden neighbour blocks. Demolition v4, EventBlocks and Balance see hidden blocks; BlockAt is an exact grid lookup. Percent now carries 4 decimals. Spawn moved to 30 studs in front of the body. | Voxel Kaiju Plan 2b ; W28 | Claude | Done | Tests 09-23: 5 dmg at a corner cracked the block into 20 exposed chunk Parts, removed the nearest chunk, dented the next, un-parked 1 hidden neighbour; full hit removed 8 Skin chunks; D9 on a chunk and D7 on a HIDDEN Event block hold; block completed after 3 hits with a scaffold; client saw 3 hits on a Light block with Model arg, pops -0.267, 25 chunk events; full clear of 35,134 blocks in 9.2 s reached 100.0000 with 0 Parts left in Kaiju and KaijuHidden. Client loads 8,258 Parts at join. | 2026-09-23
W30 | Kaiju skin Phase 1 | Built-in materials per BlockMaterial | KaijuConfig.Materials: Skin Cobblestone, Flesh Mud, Sucker Pebble, Ridge Slate, Eye Glass, Light / Event / Organ / Egg Neon. Applied to all 35,134 block Parts in place (Kaiju + KaijuHidden); Demolition gives cracked chunks the block material; EventBlocks sets Neon on retagged event blocks so buried events glow when exposed. Zero extra instances, no upload. Phase 2 (uploaded MaterialVariants, StudsPerTile 2.667) reuses the same table. | R14 ; Q27 ; P13 | Claude | Done | 09-23: re-materialed 35,134 Parts (Skin 14,782 Cobblestone, Flesh 15,282 Mud, Light 2,541 Neon, Sucker 1,620 Pebble, Ridge 805 Slate, Eye 104 Glass); 24 event blocks Neon; cracked Skin block showed 10 Cobblestone chunks; screenshots: scale plates, glowing streaks, pebbled suckers read as a creature. | 2026-09-23
W31 | Hit feel polish (research + build) | Whole-block pop, hit flash, +$ popup, Cash | Second research sweep logged in the Cutting Polish Plan 1b (wiki, Reddit, YouTube, DevForum: the whole targeted block punches, reward only on completion as a +$ popup, drones earn like players; debris / sound / curve are not documented anywhere public). Built: the client snapshots every chunk Part of the hit block and scales them together about the block centre (0.90 in 70 ms, 1.04 overshoot 90 ms, settle 60 ms), restoring the snapshot exactly; dust puff; pooled shards capped at 4 per hit; "+$N" billboard rises and fades on completion; Demolition credits RunConfig.CashPerBlock (1, provisional until Q04) to the finishing actor on a per-player Cash attribute, drones credit their owner; HUD shows "$ N"; the aim outline fills briefly on the player's own hits; Server.Cutter publishes a CutState debug attribute (NoTool / NoBlock / AimStale / Dead / OutOfReach / Refused / OK). | Cutting Polish Plan 1b, 10 ; R10-R12 ; Q04 | Claude | Done | 09-23 play-mode harness: Light block broke in 5 hits, Skin block in 6 (CutState OK on every tick); chunk scale ran 0.900 -> 1.054 -> 1.000 over 32 frames with exact restore; 1 popup and Cash +1 per broken block; 20 live shards from a pool of 60; drone kept cutting and paused only under the 40% share cap as designed. Hit flash needs a real mouse aim, checked by code review only. | 2026-09-23
W32 | Incident | Kaiju moved 90 studs after generation | Workspace.Kaiju was found 90 studs (+Z) from where it was generated while the 26,876 hidden Parts in ServerStorage.KaijuHidden stayed put, so Demolition's saved Origin was stale and every computed block centre was 90 studs off: the cutter reported OutOfReach on 36 of 37 ticks and the drone lost blocks after one hit. A second bug hid behind it: WorldPivot set on an empty Model is discarded, so cracked blocks had a wrong pivot. Fixes: Demolition.Init derives the origin from an exposed Part (and warns), hidden Parts snap to the grid when exposed, cracked-block pivots are set after the chunk Parts exist, Demolition.CenterOf gives the grid centre for any block holder; the hidden Parts and the attribute were realigned in the edit place (undo waypoint "Realign hidden blocks to moved Kaiju"). | W29 ; W31 | Claude | Done | Verified 09-23: worst CenterOf error over 500 exposed Parts 0.0000 after the fix; hidden Parts derive the same origin as exposed ones. | 2026-09-23
W33 | Analysis | Drones.txt + Understanding through drawing.pdf | Read both files Shayan added to the repo root. Drones.txt is the reference skill tree with partial prices and stats (logged as R15); the PDF is three pages of hand-drawn design notes (logged as R16): HUD layout, tool rules, five event outcomes, drone / player / gun rules. Findings turned into Q28 (Survivor / Health / UFO outcomes), Q29 (upgrade axes), Q30 (economy scale), Q31 (cutter vs larva split) and one build item, W34. | R15 ; R16 ; Q28-Q31 | Claude | Done | Analysis delivered 09-23 in chat and in the R / Q rows. | 2026-09-23
W34 | Cutter "for both" (drawing p.1) | Laser cutter damages larvae | The drawing marks the Laser Cutter "for both" and the Gun "X block". Server.Cutter now accepts an enemy part as the aim target: if the part is not a kaiju block it asks Gun.EnemyHumanoid (the same Enemy-tag check the gun uses, now exported) and applies ToolConfig.Cutter.EnemyDPS (40, provisional, Q31) x LevelMult x HitInterval per discrete hit with Humanoid:TakeDamage, same reach and CutState rules as blocks. LaserCutter client raycasts Kaiju + Enemies and outlines the enemy Model. D9 is untouched: the gun still never requires Demolition. | R16 ; Q31 ; ToolConfig.Cutter.EnemyDPS | Claude | Done | 09-23 play-mode harness: a 50 HP larva 9.8 studs away went 50 -> 0 in 1.4 s (9 hits of 6.0, CutState OK on 12 of 13 ticks, last tick NoBlock after death); gun regression: larva 50 -> 40 per shot, gun on a kaiju block left RemainingBlocks unchanged (D9). Player took no damage (larva held still). | 2026-09-23
W35 | Survivor + Health outcomes (drawing p.2, Q11) | Positive event outcomes | New Server.Pickups: EventRoll.Weights now Gas 2 / Egg 2 / Survivor 1 / Health 1 (a third of rolls positive). A rolled Survivor leaves a placeholder figure (2x5x2 Neon Part) standing on the cavity floor; the first player within 6 studs rescues them and is paid EventConfig.Pickups.Survivor.Cash (25, provisional) with the same "+$" popup as a block. A rolled Health leaves a cross (3x3x1 red Part) that heals 30 HP to the first player who reaches it. Unreached pickups vanish after 90 / 60 s. Pickups live in Workspace.Pickups, so they never count as active events for EVT-16 or the K3 event clock. Collection is a 5 Hz server distance check, no physics. Placeholders until M2 models. | R16 ; Q11 ; Q28 ; EventConfig.Pickups | Claude | Done | 09-23 play-mode: fired both outcomes from the server next to the player; walking onto the cross took HP 40 -> 70 and removed it; reaching the survivor took Cash 1 -> 26, removed it, and the client showed the popup and HUD "$ 26". 600 rolls with the no-repeat rule gave Gas 205 / Egg 179 / Survivor 110 / Health 106. UFO and the colour telegraph remain open in Q28. | 2026-09-23
W13 | B3 / LOOP-05 | HP system | Server.Health sets MaxHealth from RunConfig, StarterCharacterScripts.Health override kills passive regen, Died sets RunState.State = Failed when nobody is alive; Demolition.CanDamage refuses while State is not Running. Q09 co-op rules still open. | LOOP-05 ; D4 | Claude | Done | Play-mode test: HP held at 50 for 3 s, death flips State to Failed, cutter refused afterwards. | 2026-09-22
4. BUILD PLAN |  | Day 2 to Day 8, adjusted for what is already done and for the gaps. Ship Wed 30 Sept.
ID | Day | Item | Tasks | Depends / Needs | Owner | Status | Result | Date
P00 | Day 2 - Tue 22 Sep | Unblock | Get Q01-Q07 answered. Add the v0.3 spec to gdd/ (Q12). Decide the turret shelf (Q13). | - | Shayan | Planned
P01 | Day 2 | Gun and HP | A6 gun (D8 / D9 through Demolition.CanDamage). B3 HP, no regen, zero ends the run. B1 city grey-box. | A5 done, B2 done | Dev A / Dev B | Done | A6 gun and B3 HP built and tested 09-22 (W12, W13). B1 city grey-box waits on Shayan's models. | 2026-09-22
P02 | Day 2 | Kaiju check in engine | Pull B6 forward: verify climb routes, opening and bury volume on the real octopus (KJU-03 / 04 / 05). | M1a done | Dev B + Modeller 1 | Done | Audit done 09-22 (W08). Climb solved with scaffolds (W11); mouth opening still open (Q20). | 2026-09-22
P03 | Day 3 - Wed 23 Sep | Egg to larva, unblocked from art | A7 with a placeholder cube larva so it does not wait on M1c (fixes REL-09); swap the model when M1c lands. B5 4-slot inventory. | A3, B2 | Dev A / Dev B | Done | B5 inventory and A7 egg event with cube larva built and tested 09-22 (W14, W15). Cutting research logged (R10-R12), decision Q23 open. | 2026-09-22
P04 | Day 3 | Gas early | Move A8 gas port from Day 4 to Day 3 (fixes the 12 h Day 4 for Dev A, REL-08). | A3 | Dev A | Done | A8 gas built and tested 09-22 (W17), pulled forward from Day 4 as planned. | 2026-09-22
P05 | Day 4 - Thu 24 Sep | Mask, visibility, drone | A9 mask 4 tiers plus EVT-04 screen gas fill (Gap G04). A10 support drone with event-block exclusion plus DRN-03 peel-around. | A8, M2a, M2c | Dev A | Done | A9 mask tiers + EVT-04 gas visibility (W18) and A10 support drone with DRN-03 peel-around and N4 cap (W19), all 09-22. Day 4 dev work is complete two days early; B7 co-op spike is next. | 2026-09-22
P06 | Day 4 | Co-op spike, GO / NO-GO | B7 replicate destruction to 4 clients (mostly free after W03). Decide co-op scope. Needs Q09 and Q14. | A3, Q09, Q14 | Dev B | Planned
P07 | Day 5 - Fri 25 Sep | Co-op and HUD | B8 shared %, join / leave, death handling COOP-03 / 04 (from Q09). B9 HUD. A11 drone cap. A12 roll policy including party-size scaling EVT-17. | B7, B5, A10 | Dev A / Dev B | Partial | B9 HUD (W21) and A12 roll policy incl. EVT-17 party scaling (W20) done 09-22. A11 drone cap landed with the drone (W19). Remaining: B8 co-op shared % / join-leave and COOP-03/04 death handling, both waiting on Q09 and Q14. | 2026-09-22
P08 | Day 6 - Mon 28 Sep | Run end, lobby, shop | NEW: LOOP-03 / 04 clear sequence, reward payout, return to lobby (Gap G01). A13 healing. A14 upgrade axis plus persistence. B10 lobby. B11 shop (needs Q04 currency). | Q04, Q06, B8 | Dev A / Dev B | Planned
P09 | Day 7 - Tue 29 Sep | Measure and QA | A15 K1-K9 telemetry. A16 balance to a completable 15-min run. B12 full QA solo and 4p. B13 text brief plus first-run skip (MAP-10). | all | Dev A / Dev B | Partial | A15 telemetry (W22), A16 balance pass (W23) and B13 brief with first-run skip (W24) done 09-22. Remaining: B12 full QA pass, best run after co-op lands. | 2026-09-22
P10 | Day 8 - Wed 30 Sep | Ship | A17 bugfix. A18 verify D7 / D9 against Demolition.CanDamage. B14 publish. B15 confirm KPIs emit. | B12 | All | Planned
P11 | Ongoing | Art | M1b-M1h octopus -> larva -> drone -> polish. M2b-M2h city kit, lobby, UI art. Sketch the HUD mock (FIG-12) on Day 4 so B9 does not run ahead of it (Gap G08). | - | Modellers | Planned
P13 | Next | Kaiju skin, Phase 1 then 2 | Phase 1: KaijuConfig.Materials table (BlockMaterial -> Enum.Material), applied by the generator to block Parts and by Demolition on crack to chunk Parts; Neon for Light / Event. Phase 2: MaterialVariants in MaterialService named per BlockMaterial, part.MaterialVariant set from the same table once assets exist; artist brief: 1024 tileable colour + normal + roughness, low contrast. | Q27 ; R14 | Claude / Art | Planned
P12 | Post-MVP | Parked | Telegraphed UFO / eagle-style hazard, survivors, turrets (Progress plans), PETs, costume gacha, HARD / EXTREME, drone camera (gate on K6). | O-B ; D01 ; Supp. Notes 8 | - | Planned

## Status
Dismantle - Status |  | Done / pending as of 2026-09-23. W and Q numbers refer to the Build Plan tab; A / B / M numbers to the tasks tab. Everything marked Done exists in kaiju.rbxl AND in the repo under src/. The place file still has to be SAVED by Shayan.
1. DONE |  | Built, tested in Studio, mirrored in src/
ID | Status | Area | Item | What exists | Refs | Owner | Date
D01 | Done | Setup | Place layout: Config / Remotes / RunState, Server folder, Assets, TestArea, 3 tools with primitive handles | Setup.luau recreates all of it | A1 / B2 ; W01 ; W09 | Claude | 2026-09-22
D02 | Done | Core | Demolition with logical blocks and 2x2x2 cells, shared percent per cell, D7 / D9 gate, BlockAt, events for FX | Server.Demolition | A3 ; W04 ; W25 | Claude | 2026-09-23
D03 | Done | Tools | Laser cutter: discrete hits, cells per hit by level, hit-position clamp, beam, white outline on the logical block | Server.Cutter + LaserCutter.Client | A5 ; W05 ; W16 ; W25 | Claude | 2026-09-23
D04 | Done | Hit feel | Whole-block pop from a snapshot (0.90 in / 1.04 overshoot / settle, exact restore), dust puff, pooled shards capped per hit, +$N popup on completion, provisional Cash per block credited to the finishing actor (drone -> owner), HUD $ line, hit flash on the aimed outline, CutState debug attribute | Server.BlockFX + StarterPlayerScripts.BlockFX + LaserCutter.Client + FXConfig + RunConfig.CashPerBlock | W25 ; W31 ; Cutting Polish Plan 1b / 10 | Claude | 2026-09-23
D05 | Done | Traversal | Scaffolds: climbable truss left in every broken block, leaning on a neighbour, cleared on run end | Server.Scaffold | Q19 ; W11 | Claude | 2026-09-22
D06 | Done | Tools | Gun: unlimited ammo, enemies only, fire rate, range and spoof checks, logs | Server.Gun + Gun.Client | A6 ; W12 | Claude | 2026-09-22
D07 | Done | Core | HP: fixed max, no regen, run fails when nobody is alive, cutter refuses after failure | Server.Health + StarterCharacterScripts.Health | B3 ; W13 | Claude | 2026-09-22
D08 | Done | UI | Inventory: keys 1-4, one-press swap, slot 4 reserved, default hotbar off, plain 4-box bar | StarterPlayerScripts.Inventory | B5 ; W14 | Claude | 2026-09-22
D09 | Done | Events | Event block seeding: 24 Flesh blocks retagged Event per run, outcome rolled on break | Server.EventBlocks | EVT-01 ; Q22 ; W15 / W20 | Claude | 2026-09-22
D10 | Done | Events | Roll policy: Gas / Egg weighted, no immediate repeat, single-event phase under 30%, larvae per party 1/1/2/2, ignores hits after run end | Server.EventRoll | A12 ; W20 | Claude | 2026-09-23
D11 | Done | Events | Egg: cube larva with pathfinding chase and bite, tagged Enemy, corpse cleanup | Server.Egg | A7 ; W15 | Claude | 2026-09-22
D12 | Done | Events | Gas: sphere cloud, DPS unless mask held, InGas attribute, zone guard | Server.Gas | A8 ; W17 | Claude | 2026-09-22
D13 | Done | Tools | Gas mask: Lv1 on spawn, FOV by tier while held, green overlay heavy / light | Server.Mask + GasMask.Client + GasOverlay | A9 ; Q02 ; W18 | Claude | 2026-09-22
D14 | Done | Automation | Support drone: one per player, nearest ordinary block, discrete hits from its side, 40% share cap with pause / resume logs | Server.Drone | A10 / A11 ; Q07 ; W19 | Claude | 2026-09-23
D15 | Done | UI | HUD: percent + bar, HP + bar, GAS / LARVA edge warnings, state banner, EVENT flash | StarterPlayerScripts.HUD | B9 ; W21 | Claude | 2026-09-22
D16 | Done | Telemetry | K1-K9 as [KPI] JSON lines: RunStart, PlayerJoined, Event, phases, ReturnToCutting, Last1Percent, Down, RunEnd | Server.Telemetry | A15 ; W22 | Claude | 2026-09-22
D17 | Done | Balance | Cutter 150 DPS, 24 events, start-of-run estimate with budget warning (9.2 min pure cutting vs 9.8 budget) | Server.Balance + RunConfig | A16 ; W23 | Claude | 2026-09-22
D18 | Done | Intro | Text mission brief: narrated first run, SPACE / click skip after, DataStore-backed count with in-memory fallback | Server.Brief + MissionBrief + BriefConfig | B13 ; W24 | Claude | 2026-09-22
D19 | Done | Process | Source mirror src/ (32 scripts), Setup.luau, Restore.luau, serve.js: one-call restore after a revert | repo src/ | W26 / W27 | Claude | 2026-09-23
D20 | Done | Art | Kaiju skin Phase 1: built-in PBR materials per block material (Cobblestone skin, Mud flesh, Pebble suckers, Slate ridge, Glass eyes, Neon lights and event blocks), chunks inherit | KaijuConfig.Materials | W30 ; R14 | Claude | 2026-09-23
D21 | Done | Kaiju | Large Voxel Kaiju: 35,134 blocks of 8 studs (3x resampled octopus, 840 x 168 x 792), intact blocks as voxel Parts, hidden blocks server-side, 3x3x3 chunks on crack; Demolition v4; carry-over damage; old models backed up | Workspace.Kaiju + ServerStorage.KaijuHidden + Server.Demolition | W28 / W29 ; Voxel Kaiju Plan | Claude | 2026-09-23
D22 | Done | Research | Reference title, competitor, genre, cutting model research; Cutting Polish Plan | Build Plan R01-R13 ; Progress/modules | R01-R13 | Claude | 2026-09-22
D23 | Done | Decisions | Answered: octopus model state, Lv1 mask, drone cap enforced (prov.), scaffolds, fresh project, event seeding (prov.), internal cells | Build Plan Q01 Q02 Q07 Q19 Q21 Q22 Q23 | - | Shayan / Claude | 2026-09-23
D24 | Done | Research | Reference skill tree (Drones.txt) and Shayan's design drawing analysed; findings in R15 / R16 and Q28-Q31 | Build Plan R15 R16 | W33 | Claude | 2026-09-23
D25 | Done | Tools | Laser cutter also damages larvae (EnemyDPS 40 per level mult, discrete hits, same reach / CutState rules); client outlines enemies; Gun exports its Enemy check | Server.Cutter + Gun + LaserCutter.Client + ToolConfig | W34 ; R16 ; Q31 | Claude | 2026-09-23
D26 | Done | Events | Survivor (rescue pays $25) and Health (+30 HP) positive outcomes of an event block, rolled at a third of events, placeholder Parts, distance pickup, auto-expire | Server.Pickups + EventConfig.Pickups / Roll.Weights | W35 ; R16 ; Q11 | Claude | 2026-09-23
2. PENDING - blocked on a decision |  | Cannot start until the named question is answered
ID | Status | Area | Item | What is needed | Refs | Owner | Blocked by
P01 | Blocked | Co-op | B7 networking spike + B8 shared % / join / leave | Server model: private 4-player party or public server up to 20 | B7 / B8 ; COOP-01 / 02 | Claude | Q14
P02 | Blocked | Co-op | Death handling: spectate / respawn / downed + revive, wipe = fail? | Rules for one of four dying | COOP-03 / 04 ; Gap G03 | Claude | Q09
P03 | Blocked | Run end | Clear sequence, result screen, payout, return to lobby | What happens at 100% | LOOP-03 / 04 ; Gap G01 | Claude | Q06
P04 | Blocked | Economy | Currency model, reward tables, upgrade costs, shop prices | One currency or two (in-run cash + persistent) | ECO-01..04 ; Gap G02 | Claude | Q04
P05 | Blocked | Lobby / shop | B10 lobby deploy gate, B11 shop (masks, guns, healing), A14 upgrade axis + persistence | Currency (Q04) and purchase location (Q03) | B10 / B11 / A14 | Claude | Q04, Q03
3. PENDING - buildable now |  | No decision needed; say go
ID | Status | Area | Item | What is needed | Refs | Owner | Note
B01 | Ready | Art | Kaiju skin Phase 2: uploaded MaterialVariants (1024 tileable colour + normal + roughness, StudsPerTile 2.667) assigned by name from KaijuConfig.Materials | Artist or Creator Store PBR tiles | R14 ; Q27 ; W30 | Art lead / Claude | Phase 1 done; Phase 2 when assets exist
B02 | Ready | Core | A13 healing items: brought from lobby, found inside the kaiju | Small; one consumable tool + heal on use | A13 ; LOOP-06 / 07 | Claude | Before or after the shop
B03 | Ready | QA | B12 full QA pass: solo and 4p, both events, drone rules, tool separation | Best after co-op lands | B12 ; REL-01 | Claude | -
B04 | Ready | Ship | A17 bugfix, A18 verify D7 / D9, B14 publish + place settings, B15 confirm KPIs emit | After QA | A17 / A18 / B14 / B15 | Claude | Publishing needs the place published by Shayan
B05 | Ready | Sheet | Fix the M2c Spec cell in the tasks tab that Excel turned into a date (should read 5 / 6) | One cell | tasks tab row M2c | Claude | -
B06 | Ready | Kaiju | Q20 mouth / interior opening | Add a pocket to the model or drop KJU-04 for MVP | KJU-04 ; Q20 | Shayan / Modeller | Touches the model
B07 | Ready | Repo | Commit src/, Progress plan and the sheet to git | Shayan has not asked for a commit yet | - | Claude on request | -
4. PENDING - Shayan |  | Only you can do these
ID | Status | Area | Item | Why it matters | Refs | Owner | Note
S01 | Waiting | Place | SAVE kaiju.rbxl (Ctrl+S) and publish it | The file on disk is still the post-drone snapshot; two reverts lost work already. Publishing also turns on DataStore persistence | W10 ; W26 | Shayan | Do this first
S02 | Waiting | Spec | Add the v0.3 spec PDF to gdd/ | The task list is built on it and it is not in the repo | Q12 | Shayan | -
S03 | Waiting | Plans | Decide the turret plans in Progress/modules: shelve as post-MVP? | D6 dropped turrets | Q13 | Shayan | -
S04 | Waiting | Models | Larva rig, drone, cutter, gun, mask, hazmat suit, seaside city kit, lobby | Each swaps into one function; cubes and primitives hold the place | M1a-M2h | Shayan / Modellers | -
S05 | Waiting | Playtest | One real solo run start to finish | Only thing that validates the 15 min estimate; read the [KPI] RunEnd line | A16 ; K1 / K2 | Shayan | -
S06 | Waiting | Client | UFO cut sign-off (O-B); positive-event mix (D01); title overlap with Kaiju Cleanup | Client decisions | Q10 Q11 Q15 | Shayan / Client | -
S07 | Waiting | Design | Run length 15 min confirm (N1); acceptable solo vs 4p gap (N2) | Fixes block count and validates D2 | Q16 Q17 | Shayan | -
5. OPEN QUESTIONS AT A GLANCE |  | Answer in the Build Plan tab, column H
ID | Status | Area | Question | Options | Refs | Owner | Unblocks
Q26 | Open | Balance | How does a 35k-block kaiju clear in a run? | Raise the target, area damage per level, automation carries the bulk, or a mix | W29 | Shayan / Client | Completable run; every balance number
Q28 | Open | Events | Survivor and Health built (W35). Still open: UFO in or out (Q10)? Colour telegraph of the event type before the break? Survivor cash 25 and heal 30 right? | UFO in / out; colour hint yes / no; numbers | R16 ; Q10 ; W35 | Shayan / Client | EVT rows, event roll weights
Q29 | Open | Upgrades | Which upgrade axes for MVP: cutter rate / range, gun area of fire, drone speed? Auto Mine free? | Reference tree R15, drawing R16 | R15 ; R16 ; Q24 | Shayan / Client | Upgrade System Plan
Q30 | Open | Economy | $1 per block vs $10-$35k node prices: scale cash, prices, or pay per chunk? | Decide with Q04 and Q26 | R15 ; Q04 ; Q26 | Shayan / Client | Shop prices, Cash rule
Q31 | Open | Tools | Cutter vs larva damage: keep EnemyDPS 40 (gun 50)? | 40 / 20 / equal | W34 ; R16 | Shayan | Tool balance, Telemetry metric name
Q24 | Open | Balance | Ranges for 8-stud blocks: cutter 90 / drone 120 / gas 60 / aggro 250 still right on the big body? | Tuned for 40-stud blocks; the body is now 840 studs wide | W28 / W29 | Shayan | Feel of every tool
Q25 | Open | Traversal | Keep scaffolds now that chunk terraces are walkable? | 8-stud blocks vs 7.2-stud jump | Q19 | Shayan | Scaffold module stays or goes
Q04 | Open | Economy | One currency or two? | Reference uses in-run Cash on site + Gems in the lobby | Gap G02 | Shayan / Client | Shop, upgrades, rewards
Q06 | Open | Run end | What happens at 100%? | Result screen, payout, auto-return to lobby | Gap G01 | Shayan / Client | LOOP-03 / 04
Q09 | Open | Co-op | One of four dies: spectate, respawn, or downed + revive? Wipe = fail? | Kaiju Cleanup uses clone respawn | Gap G03 | Shayan / Client | B8, COOP-03 / 04
Q14 | Open | Co-op | Private 4-player party or public server up to 20? | Reference runs 20-player public servers | D2 | Shayan / Client | B7 / B8, lobby
Q03 | Open | Shop | Equipment in lobby, upgrades on site? | Supplementary Notes 3.2 split | - | Shayan | B11
Q10 | Open | Events | Cut the UFO laser from MVP? | Reference eagle shows a telegraphed hazard is cheap | O-B | Client | EVT-12
Q11 | Open | Events | Add a positive event so it is not crisis after crisis? | Survivors or chest-like egg outcome | D01 | Shayan / Client | EVT-18
Q05 | Open | Balance | Real block HP / cutter numbers from v0.3? | Current values are invented and self-checked by Balance | SET-04 | Shayan | Tuning
Q08 | Open | Art | Who owns cutter SFX / VFX? Damage feedback before break? | Placeholder pop + shards in place | - | Art lead | M2c / M1d
Q12 | Open | Spec | Where is the v0.3 spec PDF? | Add to gdd/ | - | Shayan | Everyone
Q13 | Open | Plans | Shelve the turret plans? | D6 dropped turrets | - | Shayan | -
Q15 | Open | Title | Concern about Kaiju Cleanup overlap? | Steam 2026, same premise | R06 | Client | Store naming
Q16 | Open | Balance | Confirm 15 min run length | Provisional | O-C | Shayan | N3 block count
Q17 | Open | Balance | Acceptable solo vs 4p clear-time gap | Only thing validating D2 | Gap G07 | Shayan | -
Q18 | Open | Tools | LaserCutter in StarterPack until inventory? (moot, inventory done) | - | - | - | Close
Q20 | Open | Kaiju | Add a mouth pocket or drop KJU-04? | Model has no cavity | KJU-04 | Shayan | -